## Agenda
Master plan: BiPlus visit to the current Ops COE in Malaysia
Day | Time | Main activity | BiPlus does | SDSAP does | RHQ does | Done when | Status | Goal | DoD | What to do
Day 1 - 27th Oct
Morning | Goal: See how the COE runs: intake, triage, assignment and the daily rhythm. | [6 empty] | Tổng quan về vận hành CoE
| 09:30 to 10:00 | Welcome | BiPlus visit lead and Service Delivery Manager meet the SDSAP COE lead: site and data rules, pairs. | Short welcome; introduce the counterparts. | None. | Everyone is seated with a counterpart. | Planned
| 10:00 to 12:00 | Daily operation | Service Delivery Manager sits beside the person who triages: how requests arrive, priority, assignment, follow-ups, shift handoffs. | Work as normal. | None. | Intake to close observed for the COE. | Planned | Quan sát, đánh giá thực tế vận hành CoE hiện tại để chỉ ra các bất cập mà BiPlus có thể giải quyết và làm tốt hơn đối tác hiện tại. | - Bản ghi hiện trạng và đánh giá trên Confluence BiPlus thực tế đối tác về: cơ sơ vật chất, layout thiết kế, tiêu chuẩn Security hiện tại, giờ làm, tổ chức người thực hiện,.. | Thao, Quốc quan sát và ghi lại toàn bộ
| 10:00 to 12:00 | Team queues | Tech Lead, QA Lead and Merchandising Sub-Leads sit beside the SDSAP leads of their teams: how work is picked up, done, checked and closed. | Work as normal. | None. | Daily work observed for Merchandising, Tech and QA. | Planned | Học cách thực tế mọi người thao tác ticket trên Jira, cách cộng tác với các stakeholder. Đánh giá khối lượng và tốc độ xử lý ticket Hiểu cách mọi người monitor và quản lý SLA Đánh giá tài liệu vận hành nội bộ | - Bản note trên Confluence ghi lại 1 ngày làm việc của 1 nhân sự - Confirm lại các tài liệu vận hành nội bộ | - Ngồi cùng và ghi note lại theo ticket toàn bộ quá trình thực hiện và đưa lên Wiki nội bộ - Comment các điểm cần cải tiến tài liệu vận hành nội bộ
| 10:00 to 12:00 | Markets | Merchandising Sub-Leads sit beside the person who handles each market: live queue, requesters, channels, language. | Work as normal. | None. | Live queue seen for all eight markets. | Planned | Học cách thực tế Lead/Sub-Lead quản lý toàn bộ Ticket và SLA. Học cách điều hành phân bổ lượng ticket khi bình thường hoặc peak, cách trao đổi với thị trường như sai priority,… Học cách điều phối tăng/giảm nguồn lực khi có các tình huống absent,.. | - Báo cáo thực tế quy trình, quy định, hướng dẫn quản lý ticket và SLA
Afternoon | Goal: See the main request types done on live tickets.
| 13:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe product, price, promotion, voucher and stock setup for each market, and the checks before QA. | Work as normal. | None. | Main request types observed for each market. | Planned | Hiểu cách handle ticket theo danh sách ưu tiên đã plan để align với mục tiêu ramp-up load dần vào tháng 11 Hoàn thành tài liệu nội bộ cho nhân sự CoE có khả năng thực hiện service theo tài liệu. | - Từng Service Pack trên Confluence BiPlus được xác nhận để ban hành chính thức vào sử dụng. - Comment lại các điểm cần chỉnh sửa để a David Bui ở nhà sửa | - Xác định ticket mới là sẽ cần thực hiện theo service nào? - Kiểm tra lại nội dung trên Service Pack có đúng thực tế không -> comment các điều chỉnh lại
| 13:30 to 17:00 | Tech | Tech Lead and Tech Sub-Lead observe configuration requests and production change (PC) tickets. | Work as normal. | None. | Configuration and change observed. | Planned | Hiểu cách handle ticket theo danh sách ưu tiên đã plan để align với mục tiêu ramp-up load dần vào tháng 11 Hoàn thành tài liệu nội bộ cho nhân sự CoE có khả năng thực hiện service theo tài liệu. | - Từng Service Pack trên Confluence BiPlus được xác nhận để ban hành chính thức vào sử dụng. - Comment lại các điểm cần chỉnh sửa để a David Bui ở nhà sửa | - Xác định ticket mới là sẽ cần thực hiện theo service nào? - Kiểm tra lại nội dung trên Service Pack có đúng thực tế không -> comment các điều chỉnh lại
| 13:30 to 17:00 | QA | QA Lead and QA Sub-Lead observe QA checks and returns to Merchandising. | Work as normal. | None. | QA checks and returns observed. | Planned | Hiểu cách QA Team phối hợp với các team khác. Xây dựng OLA nội bộ BiPlus đáp ứng SLA Hiểu cách handle ticket theo danh sách ưu tiên đã plan | - Confirm lại tài liệu vận hành của BiPlus. Comment các điểm chưa phù hợp cần điều chỉnh - Xác nhận nội dung mục QA checklist, test case ở từng service
| 13:30 to 17:00 | Operations | Service Delivery Manager observes SLA monitoring, follow-up of tickets waiting on Samsung L2/L3, and approvals (PC, Knox). | Work as normal. | Available online for questions BiPlus should not take to SDSAP. | SLA monitoring and approvals observed. | Planned | Nắm được vận hành CoE trong các tình huống đặc biệt như holidays Nắm lại các lịch phải họp hành, báo cáo cho các thị trường và RHQ. Hỏi thêm về các meeting Ad-hoc
Day 3 | Goal: See the harder situations: urgent requests, escalations, launches. | [6 empty] | Nắm danh sách các dashboard, các filter cho cả CoE, các team và individual (nếu có) Ngoài các hệ thống Jira, Confluence và Mastermost ra thì trên máy có sử dụng tool nào khác hỗ trợ công việc không. Hiểu cách sử dụng AI hiện tại
| 09:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe urgent requests, bulk updates, AEM and Shop App content, and EPP, SMB, O2O and 3PD store requests. | Work as normal; call the BiPlus person over when an urgent or unusual request comes in. If there is no urgent request, reopen some previous requests to explore. | None. | Urgent and bulk work observed. | Planned
| 09:30 to 15:30 | Tech | Tech Lead and Tech Sub-Lead observe order issues, integrations, escalation to Samsung L2/L3 and account requests. | Work as normal; let BiPlus sit in on escalations. | None. | Order issues and escalation observed, if they occur. | Planned | Hiểu cách handle ticket theo danh sách ưu tiên đã plan để align với mục tiêu ramp-up load dần vào tháng 11 Hoàn thành tài liệu nội bộ cho nhân sự CoE có khả năng thực hiện service theo tài liệu. | - Từng Service Pack trên Confluence BiPlus được xác nhận để ban hành chính thức vào sử dụng. - Comment lại các điểm cần chỉnh sửa để a David Bui ở nhà sửa | - Xác định ticket mới là sẽ cần thực hiện theo service nào? - Kiểm tra lại nội dung trên Service Pack có đúng thực tế không -> comment các điều chỉnh lại
| 09:30 to 15:30 | QA | QA Lead and QA Sub-Lead observe a BVT or a sanity test, if one runs this week. | Work as normal; let BiPlus sit in on a BVT or sanity test, if one runs. | None. | BVT or sanity test observed, if one runs. | Planned | Hiểu cách handle ticket theo danh sách ưu tiên đã plan để align với mục tiêu ramp-up load dần vào tháng 11 Hoàn thành tài liệu nội bộ cho nhân sự CoE có khả năng thực hiện service theo tài liệu. | - Từng Service Pack trên Confluence BiPlus được xác nhận để ban hành chính thức vào sử dụng. - Comment lại các điểm cần chỉnh sửa để a David Bui ở nhà sửa | - Xác định ticket mới là sẽ cần thực hiện theo service nào? - Kiểm tra lại nội dung trên Service Pack có đúng thực tế không -> comment các điều chỉnh lại
| 09:30 to 17:00 | Operations and leadership | Service Delivery Manager observes urgent issues and incidents, if any. BiPlus visit lead sits in on RHQ or subsidiary calls with the COE, if any, listen only. | Let BiPlus listen in where suitable. | Agrees that BiPlus may listen in on RHQ calls with the COE this week. | Incident and call handling observed, if they occur. | Planned | Hiểu cách QA Team phối hợp với các team khác. Hiểu cách handle ticket theo danh sách ưu tiên đã plan | - Xác nhận nội dung mục QA checklist, test case ở từng service
Day 4 | Goal: See open work and how each market differs. | [6 empty] | Hiểu cách điều hành, quản lý các loại ticket urgent, hay PO. Hiểu cách họp đột suất, bổ sung ngoài lịch cố định Hiểu cách xử lý khi có tình huống thất thoát xảy ra
| 09:30 to 15:30 | Open work per market | Merchandising Sub-Leads observe open tickets and pending work for each market. Tech Lead and Tech Sub-Lead observe open Tech work by market. | Work as normal. | None. | Pending work seen for each market. | Planned
| 09:30 to 17:00 | Peak days | Merchandising and QA observe preparation for 11.11, Black Friday and Cyber Monday, and any launch this week. | Work as normal. | None. | Peak preparation observed. | Planned | Hiểu cách xử lý ticket kéo dài, bị pending lâu
| 09:30 to 12:30 | Backlog and tools | Service Delivery Manager observes how the backlog is reviewed, and the tools, filters and channels used every day. | Work as normal. | None. | Backlog routine and tools observed. | Planned | Hiểu quy luật khi nào thì có lượng ticket tăng đột biến Hiểu cách xử lý ticket trong các ngày Khuyển mại lớn
Day 5 | Goal: Fill in situations not seen yet; agree the November plan; close the visit.
| 09:30 to 12:30 | Situations not seen yet | Each BiPlus person observes the situations not yet seen during the week. | Work as normal. | None. | As many situations as possible observed. | Planned | Chốt được chiến thuật và kế hoạch, phạm vi giữa 3 bên để tháng 11 BiPlus bắt đầu tiếp nhận xử lý ticket. Thống nhất các tính huống phát sinh, quản lý rủi ro Thống nhất kênh giao tiếp và escalation | Bản kế hoạch riêng được share trên Google Sheet để 3 bên nắm và điều hành
| 14:00 to 15:30 | November plan: overlap and load ramp-up | BiPlus visit lead and the team Leads share what was observed and propose the load BiPlus takes in each of the four sprints, per team (Merchandising, Tech, QA), starting from the RHQ transition plan. | Confirms the work it keeps in each sprint, how it reviews BiPlus work during the overlap, and who covers 11.11, Black Friday and Cyber Monday. | Chairs the meeting. Agrees the load share for Sprints 1 to 4 per team, the SLA owner in each sprint, and the sprint rhythm: retrospective, improvements and plan for the next sprint. | Load ramp-up for the four sprints and the sprint rhythm agreed by RHQ, SDSAP and BiPlus, and written in the meeting note. | Planned
| 15:30 to 16:30 | Thank-you and wrap-up | BiPlus visit lead thanks SDSAP and asks for one contact per team for short questions until 30 November. | Name contacts, if willing. | Receives a short observation summary after the visit. | Visit closed. | Planned
After the visit | Goal: Use what was observed; take over the load sprint by sprint.
| To 30 November | Follow-up | Send a short observation summary to RHQ within one working day. Turn notes into BiPlus runbooks and training. | Answer short questions if contacted. | Forward questions to SDSAP if needed. | Observations used in Academy training and Sprint 1. | Planned
| End of each sprint (Sprints 1 to 4) | Sprint retrospective and plan | Present the sprint results (work taken over, SLA, quality, issues), the improvements for the next sprint, and the proposed load for the next sprint. | Gives feedback on BiPlus work in the sprint and confirms the work it hands over next. | Chairs the meeting. Agrees the improvements and the load share for the next sprint. | Next sprint plan agreed; every improvement has an owner. | Planned

## Training
Session # | Date | Time | Component | Title | PIC | Confluence | Status | Participants | BiPlus comments
| 2026-10-23 |  | Process | COEC JIRA Operation and Workflow | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/436443708/Subsidiary+Section | COMPLETED | CoE All team
| 2026-10-23 |  | Process | SOP and Merchandising Handbook | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/436443708/Subsidiary+Section | COMPLETED
| 2026-10-23 |  | Process | Standard Template | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/454182529/Merchandising+Standard+Template | COMPLETED
| 2026-10-23 |  | Process | BVT SOP and Staging Data Compilation | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/508777939/Merchandising+BVT | COMPLETED
| 2026-10-23 |  | Process | All JIRA Dashboard and Filter | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/697087366/Merchandising+JIRA+Dashboard+and+filter | COMPLETED
| 2026-10-26 |  | Product | SKU Fundamental Setup | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/586632491/KB+-+Normal | COMPLETED
| 2026-10-26 |  | Product | SKU atuto creation from AEM | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/502040999/Auto+SKU+creation+on+Hybris+from+AEM | COMPLETED
| 2026-10-26 |  | Product | Z-code, F-code Setup | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/457385246/KB+-+SEAO+Z-code+Setup+Standardisation | COMPLETED
| 2026-10-26 |  | Product | Super Sync | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/490777718/Merchandising+Onboarding+Programme | COMPLETED
| 2026-10-27 |  | Product | Benefit | Ong Hee Hui | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/581426818/KB+-+Benefits+V4.0
| 2026-10-27 |  | Product | Add-on Page with AEM additional Info | Ong Hee Hui | KB - Product Reference - Bundle and Gift https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444930309/KB+-+Add-on+Page+Gift+Selection KB - eVoucher Page and Promo Setup
| 2026-10-27 |  | Product | Pre-order setup and RTF Override | CHONG HAW EONG Saidatul Humairah Binti Abdul Razak | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/632006428/ID+RTF+Override
| 2026-10-27 |  | Product | Category Structure | Ong Hee Hui | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444929715/Category+Structure
| 2026-10-27 |  | Product | Auto MBO - config - benefit | Shamni Krishnan Saidatul Humairah Binti Abdul Razak | KB - Automated Addon Page Discount (Auto MBO)
| 2026-10-27 |  | Process | Knox Approval | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/508788720/KB+-+Special+Price+Knox+Approval https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/512074055/KB+-+Promotion+Rule+Knox+Approval
| 2026-10-27 |  | Added Service | Overtade | Ong Hee Hui | KB - [NZ] Enhanced Overtrade
| 2026-10-27 |  | Added Service | Trade-up | Jenardi Alvindo Girsang | Bulk Upload CE Trade-up (Revamp)
| 2026-10-27 |  | Added Service | Trade-in setup (With T-base code) | Lee Chia Yee Tai Sheau Yann | KB - Bulk Upload Product Reference - [SEAO] COE & Projects - Confluence [AU] T-BASE - [SEAO] COE & Projects - Confluence [ID] T-BASE - [SEAO] COE & Projects - Confluence [MY] T-BASE - [SEAO] COE & Projects - Confluence [NZ] T-BASE - [SEAO] COE & Projects - Confluence [PH] T-BASE - [SEAO] COE & Projects - Confluence [SG] T-BASE - [SEAO] COE & Projects - Confluence [TH] T-BASE - [SEAO] COE & Projects - Confluence [VN] T-BASE - [SEAO] COE & Projects - Confluence
| 2026-10-27 |  | 3PD | 3PD E2E flow, issues management, cronjobs, etc… for all middleware | Quan Nguyen | KB - 3PD*
| 2026-10-27 |  | Fulfillment | priority warehouse by subs configs | Manikanta Vaddisetti | SAVINA: Preferred warehouse priority
| 2026-10-27 |  | Fulfillment | Delivery mode/service configs by sub by site by product | Mohammad Ashhar Mushtaq
| 2026-10-27 |  | Fulfillment | Order processes E2E | Aldwin John Gavino | D2C COE - Order Remediation
| 2026-10-27 |  | Fulfillment | Warehouse setup by sub by subs | Manikanta Vaddisetti
| 2026-10-27 |  | Config | Direct EA access | TAN SOON KIT AMOS | PC-32611 - Jira issue doesn't exist or you don't have permission to view it. Impex EA Direct Access User Guide Guide O2O EA Web Direct
| 2026-10-27 |  | Config | GCIC updates (ID) | TAN SOON KIT AMOS | PC-47357 - Jira issue doesn't exist or you don't have permission to view it. Technical Design Document - IDME-5636 "Maintenance Service" & "Extended Warranty" for CE: Bundle
| 2026-10-28 |  | Fulfillment | Leadtime master | Swalehat Ummus Shamni Krishnan
| 2026-10-28 |  | Fulfillment | Xdock | Swalehat Ummus
| 2026-10-28 |  | Product | SC+ Grading (TH) | Kasma Sama-Air | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444930748/TSE+Tradein+TradeUP+Grading+Register+New+Model
| 2026-10-28 |  | Product | SC+ MX/CE | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/619375555/KB+-+PH+CE+SC+Bundle+Monthly CE SC+ Standalone Setup Guide
| 2026-10-28 |  | Product | SC+ MX/CE on 3PD platform | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/674283359/KB+-+MY+CE+SC+Special+Setup+for+3PD
| 2026-10-28 |  | Product | OOW | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/586633425/KB+-+OOW+Out+of+Warranty
| 2026-10-28 |  | Product | RNPL | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444930420/RNPL+SR
| 2026-10-28 |  | Product | AU SIM | Fairoza Izzati Binti Noor Hisham | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/440485329/SEAU+SIM+Plan
| 2026-10-28 |  | Content | All scripting | TAN SOON KIT AMOS | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/687735128/Scripting
| 2026-10-28 |  | Fulfillment | NERP configs by subs by site | Mohammad Ashhar Mushtaq
| 2026-10-28 |  | Content | Email CMS | Swalehat Ummus
| 2026-10-28 |  | Content | VN SMS OTP/Notifications | Manikanta Vaddisetti
| 2026-10-28 |  | Content | PH SMS/Viber OTP/Notifications | Shamni Krishnan
| 2026-10-28 |  | Log | Kibana Log | Mohammad Ashhar Mushtaq | KB - Kibana log - [SEAO] COE & Projects - Confluence
| 2026-10-28 |  | Config | Overselling RTF - Config | Swalehat Ummus | Pre-order/Pre-order Overselling RTF Interface - [SEAO] COE & Projects - Confluence
| 2026-10-29 |  | Campaign | EPP Referral | CHONG HAW EONG | EPP Referral Programme Setup Guide + User Journey - Samsung eStore Platform Operation and Enhancement - Confluence
| 2026-10-29 |  | Multistore | Bulk order site config and Bulk Order Upload | NUR EFNI BINTI AMBRIZAL | Updated Bulk Store EPP - [SEAO] COE & Projects - Confluence https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/617668789/Bulk+order+site+config+and+feature
| 2026-10-29 |  | Price | Price Row | Ong Hee Hui | Special Price Upload V4 (1).pptx
| 2026-10-29 |  | Price | Discount Row | Ong Hee Hui | Discount Row logic (1).pptx
| 2026-10-29 |  | Promotion | Promotion simulator | Woody Yoo | Promotion Simulator Guide - [SEAO] COE & Projects - Confluence
| 2026-10-29 |  | Promotion | All promotions - Priority Scheme - Promotion rule sample | Siti Nur Farhanah Binti Mohd Noor LEE MAY YIE | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444930499/VN+-+Common+Promotion+Setup https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/439469605/AU+-+Common+Promotion+Setup https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/695889203/NZ-+Common+Promotion+Setup https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444930509/SG+-+Common+Promotion+Setup https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444930497/TH+-+Common+Promotion+Setup https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/697088558/PH+-+Common+Promotion+Setup https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/697088553/MY+-+Common+Promotion+Setup https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/697100811/ID+-+Common+Promotion+Setup
| 2026-10-29 |  | Promotion | Coupon Single Code VS Multicode External Serial Coupon Coupon Ingestion | CHONG HAW EONG | Coupon - [SEAO] COE & Projects - Confluence KB - Serial Voucher Code GCDM Ingestion - [SEAO] COE & Projects - Confluence
| 2026-10-29 |  | Promotion | Coupon display and Usergroup | Siti Sarah Binti Azman | Coupon - [SEAO] COE & Projects - Confluence https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/620243061/KB+-+Coupon+Usergroup+Setup+HGE-11315
| 2026-10-29 |  | Config | Coupon config Limit Invalidation | Aldwin John Gavino
| 2026-10-29 |  | Multistore | Open EPP + AEM | Ong Hee Hui NUR EFNI BINTI AMBRIZAL | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/687342722/Open+EPP+Hybris+EPP+AEM+Config
| 2026-10-29 |  | Multistore | EPP Multi login | Marcus Ng TAN SOON KIT AMOS | EPP login type Multi-login-type within 1 EPP site
| 2026-10-29 |  | Config | All SEAO Cronjob | Aldwin John Gavino Manikanta Vaddisetti | KB - Cronjobs - [SEAO] COE & Projects - Confluence
| 2026-10-29 |  | Config | Samsung rewards -Enable Rewards for site | Aldwin John Gavino
| 2026-10-29 |  | Config | Split S/O | Swalehat Ummus Tai Sheau Yann | CS-1141 Split Consignment Based on RDD ¦ Tied FOC inside 1 Consignment with it's Main Product ¦ PH Version - [SEAO] COE & Projects - Confluence
| 2026-10-29 |  | Config | Samsung Vault (Saved card payment), mypage and cart page | Swalehat Ummus
| 2026-10-29 |  | Config | FI Posting | Mohammad Ashhar Mushtaq | Create NERP FI & NERP Config - [SEAO] COE & Projects - Confluence Push Orders to Cancelled with FI Posting - [SEAO] COE & Projects - Confluence KB - RNPL FI Posting - [SEAO] COE & Projects - Confluence
| 2026-10-30 |  | Multistore | EPP Watermark | CHONG HAW EONG | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/508784610/Enable+watermark+on+EPP+sites
| 2026-10-30 |  | Multistore | EPP - Strcuture and Login Type, EPP Checklist | Siti Nur Farhanah Binti Mohd Noor | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/444929927/Country+EPP+Structure
| 2026-10-30 |  | Multistore | SMB -SMB Promotion | Jenardi Alvindo Girsang | KB - SG SMB Promo Setup for Prescribed Goods and Non-Prescribed Goods
| 2026-10-30 |  | Multistore | O2O/EA - Config and user journey | Azreen Bin Aziz | O2O Fake > EA Platform EPP verification for EA sites IMEI scanner for O2O site (Cart Page IMEI / SERIAL Field) -SAVINA KB - TH EA APP Guide O2O EA Cockpit
| 2026-10-30 |  | Multistore | EPP CMS - Country EPP structure - All AEM component | Siti Sarah Binti Azman Thananya Phattanatreekup | https://confluence.secext.samsung.net/spaces/SEAORHQ/pages/591792233/KB+-+Homepage+Offer+Offer+Detail+PF+Components
| 2026-10-30 |  | Integration | All third party integrations Trade-in vendors Payment vendors | Manikanta Vaddisetti
| 2026-10-30 |  | Config | Specific Topic Handover by Tech PIC | Manikanta Vaddisetti Aldwin John Gavino Mohammad Ashhar Mushtaq Swalehat Ummus Shamni Krishnan TAN SOON KIT AMOS

## Quocdm
Master plan: Quocdm - Services Delivery Manager
Item | Content
Role | Service Delivery Manager: heads the CoE in Hanoi and manages the three teams: Merchandising, Tech and QA.
Visit objectives | - Fully understand how SDSAP currently runs operations for Samsung SEAO: what the three teams do every day (intake, assignment, coordination, follow-up, handling, escalation) - The meeting and reporting rhythm - What the subsidiaries require us to guarantee - The working rules agreed between SDSAP, the subsidiaries and RHQ.
Approach | - Observe first, ask later; ask to confirm ('is this the right way?'), not to learn from scratch. - Collect questions and ask them during quiet moments or in the 1-1s. - Questions that are RHQ's to answer go to RHQ, not to SDSAP.
Security rules | - No phone screenshots, no copying or exporting Samsung data, no recording of PII. - Take notes at the level of processes, roles and aggregate figures only. - Never put notes containing Samsung data into any AI tool.
Weekly working rhythm | 08:45 BiPlus huddle → 09:30–17:00 observe and ask per the agenda → 17:15 BiPlus debrief → daily summary sent internally to BiPlus before 21:00.
Output | Description |  |  | DoD
O1. As-Is operating flow | Operating flow from intake to ticket closure for the COE and each team (Merch, Tech, QA). |  |  | Steps, roles, tools and decision points are documented.
O2. Contact map | RHQ, 8 subsidiaries, L2/L3, Spoke, 3PD, SDSAP. |  |  | 8/8 markets have details of their requester, approver and escalation contacts.
O3. RACI for 6 processes | Shop Merchandising Request, Maintenance Request, PC Ticket, Knox, Incident, BVT, Reporting. |  |  | Each process has a named contact who receives information and reports, responds and approves.
O4. Meeting and reporting map | All recurring meetings and reports. |  |  | Each line has frequency, chair, attendees, content and data source.
O5. Escalation matrix and incident flow | By situation × level × time × channel. |  |  | A list of contacts for each flow exists and is confirmed as current by the SDSAP team or RHQ (Oliver?).
Day | Time | Main activity | BiPlus does (SDM) | SDSAP does | RHQ does | Done when | Status
Day 1 | Goal: See how the COE runs: intake, triage, assignment and the daily rhythm. (SDM arrives in the afternoon.)
| Morning | Travel VN to MY | SDM flies to MY. Visit lead covers the 09:30 welcome alone: site and data rules, pairs, this week's call list, two 45-minute 1-1 slots for SDM with the SDSAP COE lead (Day 3, Day 4). | Short welcome; introduce the counterparts. | None. | Team seated; call list and SDM 1-1 slots booked. | Moved
| 14:30 to 15:00 | SDM meets the SDSAP COE lead | [Ask] Short intro: confirm the 1-1 slots, the call list and who triages today. | COE lead meets the SDM; introduces the triage person. | None. | SDM seated beside the triage person. | Planned
| 15:00 to 17:00 | Daily operation (part 1) | [Observe] Beside the person who triages: channels, priority, assignment, check for tickets without an owner. [Ask] Daily volume by market and team. | Work as normal. | None. | First half of the intake flow sketched. | Planned
| 17:15 to 18:00 | Debrief | [Coordinate] BiPlus Leads brief the SDM on the morning (team queues, 8 markets); agree tomorrow's priorities. | None. | None. | SDM up to date; all 8 markets seen by the team. | Planned
Day 2 | Goal: See the main request types done on live tickets.
| 09:30 to 11:00 | Daily operation (part 2) | [Observe] Follow-up to close; shift handoff. [Ask] Actual response time; tickets that arrive out of hours (AU, NZ); daily report (to whom, when, which figures). | Work as normal. | None. | Intake-to-close flow confirmed by the triage person. | Planned
| 11:00 to 12:30 | Operations | [Observe] SLA monitoring, follow-up of tickets waiting on L2/L3, PC and Knox lead times. [Coordinate] Send RHQ the questions not for SDSAP (subsidiary channel, last-minute cut-off). | Work as normal. | Available online for questions BiPlus should not take to SDSAP. | SLA routine and approval lead times noted; RHQ questions sent. | Planned
| 13:30 to 15:00 | Hand-offs between teams | [Follow] With the Merch, Tech and QA pairs: one ticket each that moved between teams; waiting time, QA return reasons. | Work as normal. | None. | Real hand-off times and main bottlenecks known. | Planned
| 15:00 to 17:00 | Subsidiary contacts | [Ask] With the market handlers (with Merch Sub-Leads): requester, approver and escalation contact per market; channel, hours, language, habits, unwritten agreements. [Ask] SLA for the last 3 months, top breach reasons. | Answer short questions. | None. | Contact map drafted for 8 markets. | Planned
Day 3 | Goal: See the harder situations: urgent requests, escalations, launches.
| 09:30 to 12:30 | Escalations and incidents | [Ask] Draw the escalation path with the COE lead: who, when, how fast, out of hours. [Observe] A live urgent request or incident; if none, walk through a past one up to the RCA. | Let BiPlus sit in; reopen a past case if none comes in. | None. | Escalation path and incident flow confirmed by SDSAP. | Planned
| 13:30 to 15:00 | RHQ or subsidiary calls | [Follow] Visit lead and SDM listen in: agenda, figures asked, decisions, follow-ups. | Let BiPlus listen in. | Agrees that BiPlus may listen in. | Call structure and RHQ hot topics noted. | Planned
| 15:00 to 16:00 | 1-1: meetings, reports, roles | [Ask] COE lead: every recurring meeting and report (weekly, monthly, quarterly, BVT, RCA, aging), their figures and sources; who requests, approves and decides exceptions; do's and don'ts with RHQ. | COE lead joins the 1-1. | None. | Meeting and report calendar and roles table confirmed by SDSAP. | Planned
Day 4 | Goal: See open work and how each market differs.
| 09:30 to 12:30 | Backlog and tools | [Observe] Backlog and aging review; Jira filters, dashboards and channels used every day; access BiPlus still lacks. | Work as normal. | None. | Dashboard list sent to Hanoi the same day; access gaps listed. | Planned
| 13:30 to 15:00 | Peak days | [Follow] With Merch and QA: readiness for 11.11, Black Friday and Cyber Monday per market, and who covers. | Work as normal. | None. | Peak readiness and coverage gaps listed. | Planned
| 15:00 to 16:00 | 1-1: internal cascade | [Ask] How the COE lead sets priorities for leads; how leads assign and track members; what must be escalated at once; open commitments to subsidiaries. | COE lead joins the 1-1. | None. | Cascade COE lead > lead > member described; open commitments listed. | Planned
| 16:00 to 17:30 | Prepare the November plan | [Coordinate] With BiPlus Leads: per team, work that is safe / needs supervision / not ready; draft load per sprint against the RHQ transition plan. | None. | None. | Draft for Day 5 approved by the visit lead. | Planned
Day 5 | Goal: Fill in situations not seen yet; agree the November plan; close the visit.
| 09:30 to 12:30 | Situations not seen yet | [Ask] Close the open questions; confirm the contact map, calendar and escalation path with SDSAP. | Work as normal. | None. | At most 5 open questions left, each with an owner. | Planned
| 14:00 to 15:30 | November plan: overlap and load ramp-up | [Coordinate] Present what was observed, the proposed load per team and sprint, the SLA owner per sprint and the sprint rhythm. | Confirms the work it keeps, how it reviews BiPlus work, and who covers 11.11, Black Friday and Cyber Monday. | Chairs. Agrees the load share, SLA owner and sprint rhythm. | Agreed by RHQ, SDSAP and BiPlus and written in the meeting note. | Planned
| 15:30 to 16:30 | Thank-you and wrap-up | [Ask] One SDSAP contact per team for short questions until 30 November. | Name contacts, if willing. | Receives a short observation summary after the visit. | Contacts named; visit closed. | Planned
After the visit | Goal: Use what was observed; take over the load sprint by sprint.
| By 02/11 | Follow-up | Send the observation summary to RHQ. Update CM-13, runbooks and dashboards from the gaps found. | Answer short questions if contacted. | Forward questions to SDSAP if needed. | Summary sent; changes in place for Sprint 1. | Planned
| End of each sprint | Sprint retrospective and plan | Present sprint results (work taken over, SLA, quality, issues), improvements and proposed load for the next sprint. | Gives feedback and confirms the work it hands over next. | Chairs. Agrees improvements and load share. | Next sprint plan agreed; every improvement has an owner. | Planned
Question bank
ID | Group | Suggested question | Ask / work with | DoD (done when) | Output | Status | Answer / notes
A. Intake – triage – assignment
A02 | A. Intake – triage – assignment | Who triages, on which shift? What rules decide Merch vs Tech vs QA and the priority? Who is allowed to change a priority? | SDSAP triage person (day shift) | A triage decision table (condition → team / priority) checked on at least 10 real tickets and confirmed by SDSAP. | Triage decision table | Planned
A03 | A. Intake – triage – assignment | How is work assigned – by market, skill, load or round-robin? Who assigns, and is it always done via the Jira assignee? | SDSAP triage person; SDSAP Merch/Tech/QA leads | Assignment rule written in 5 lines or fewer per team, with exceptions, confirmed by SDSAP. | Assignment rule | Planned
A04 | A. Intake – triage – assignment | What is the typical daily volume per market and per team, and when are the peak hours and peak days? | SDSAP COE Lead; triage person | Estimated volume table by market × team × time slot, enough to size Sprint 1 (Merch ~20% ≈ 20–30 tickets/day). | Volume baseline | Planned
A05 | A. Intake – triage – assignment | How do you spot tickets nobody has picked up yet (APPROVED-ES, NEW)? How often do you check and who owns it? | SDSAP triage person (day shift) | Mechanism, frequency and owner are clear; compared with the BiPlus standard (filter every 30 minutes). | Note on the unowned-ticket check | Planned
A06 | A. Intake – triage – assignment | What is your actual initial response time? What happens to tickets that arrive outside your working hours, e.g. early AU/NZ requests? | SDSAP COE Lead | Average response time and out-of-hours handling described; gap BiPlus must cover identified (24/7 shifts). | Initial response baseline | Planned
A07 | A. Intake – triage – assignment | What must be in a ticket before you start? When something is missing, how do you ask the subsidiary and move the ticket? | SDSAP Merch lead; market handler | Definition-of-Ready checklist for 3–5 main request types, plus the question templates used with subsidiaries. | DoR checklist per request type | Planned
A08 | A. Intake – triage – assignment | What shifts do you run, and how is the handover done – written or verbal? Where is the handover note kept? | SDSAP COE Lead; SDSAP shift lead | Shift model, current handoff items and differences from the BiPlus template described. | Handoff comparison: SDSAP vs BiPlus | Planned
B. Coordination – SLA monitoring – handling – escalation
B01 | B. Coordination – SLA monitoring – handling – escalation | How do you monitor SLA day to day – which filters or dashboards, who looks at them and how often? Do you use any early-warning thresholds? | SDSAP COE Lead; SLA monitor | List of SLA views, owner, frequency and action; mapped to the BiPlus 50/70/85/95% thresholds. | Current SLA monitoring vs BiPlus | Planned
B02 | B. Coordination – SLA monitoring – handling – escalation | What did SLA look like over the last three months, by team and market? What are the top three reasons for breaches? | SDSAP COE Lead | Baseline SLA figures, top 3 causes and riskiest market known; added to the risk log. | SLA baseline and breach causes | Planned
B03 | B. Coordination – SLA monitoring – handling – escalation | Who follows up tickets waiting on Samsung L2/L3, how often and through which channel? How long does L2/L3 usually take? | SDSAP Tech lead | L2/L3 follow-up routine, contacts and actual response time known. | L2/L3 follow-up routine | Planned
B04 | B. Coordination – SLA monitoring – handling – escalation | How long do PC tickets usually wait for approval? How are you handling it while Oliver is away, and what is the path for an urgent P0/P1? | SDSAP Tech lead; SDSAP COE Lead | PC lead time, urgent P0/P1 route and how to plan go-lives around the wait are known. | Note on PC approval lead time | Planned
B05 | B. Coordination – SLA monitoring – handling – escalation | How do you track Knox approvals, and how long do they take by market and division? What do you do if approval is late close to go-live? | SDSAP Merch lead | Knox tracking method, average time and fallback when late known; status convention agreed. | Note on Knox tracking | Planned
B06 | B. Coordination – SLA monitoring – handling – escalation | When Merchandising needs Tech or QA, how long does the hand-off usually take and where does it get stuck? | SDSAP Merch, Tech, QA leads | Actual OLA between teams, 3 bottlenecks and a proposed internal OLA for BiPlus. | OLA baseline and bottlenecks | Planned
B07 | B. Coordination – SLA monitoring – handling – escalation | What share of tickets does QA send back, for what reasons, and how is that fed back to Merchandising? | SDSAP QA lead | Return rate and top reasons known; BiPlus QA Lead adds them to the Merch self-check list. | QA return rate baseline | Planned
B08 | B. Coordination – SLA monitoring – handling – escalation | Could you draw your escalation path for me – who escalates to whom, for which situations, how quickly, and who is called out of hours? | SDSAP COE Lead | Escalation matrix (situation × level × time × channel) confirmed by the SDSAP COE Lead. | As-Is escalation matrix | Planned
B09 | B. Coordination – SLA monitoring – handling – escalation | How do you run an incident – who leads, how do you inform RHQ and the subsidiaries, and when is the RCA due? | SDSAP COE Lead; SDSAP Tech lead | Incident flow, notification template and RCA deadline known, checked on at least 1 real case. | As-Is incident flow | Planned
B10 | B. Coordination – SLA monitoring – handling – escalation | Have there been recent breaches or strikes? What caused them and what changed afterwards? | SDSAP COE Lead | 3–5 lessons learned added to known errors / runbooks. | Lessons learned list | Planned
B11 | B. Coordination – SLA monitoring – handling – escalation | How do you handle and count last-minute requests? Is there a cut-off time that the subsidiaries respect? | SDSAP Merch lead | Rule, counting method and actual cut-off known; open point CM-13 #7 confirmed. | Last-minute request rule | Planned
B12 | B. Coordination – SLA monitoring – handling – escalation | How do you prepare for 11.11, Black Friday and Cyber Monday – staffing, freeze, war room, midnight go-live checks? | SDSAP COE Lead; Merch & QA leads | Campaign list per market, readiness and people on duty known; used in the Day 5 coverage proposal. | Peak readiness list | Planned
B13 | B. Coordination – SLA monitoring – handling – escalation | When a subsidiary is unhappy, how does it reach you and who handles it? Do you measure satisfaction? | SDSAP COE Lead | Complaint handling flow and contacts known; handed to the future CSM. | Complaint handling note | Planned
C. Recurring meetings and reports
C01 | C. Recurring meetings and reports | Could you list every recurring meeting with RHQ – when, on which channel, who chairs, who attends, the usual agenda and who writes the minutes? | SDSAP COE Lead | Each meeting has frequency, time, channel, chair, attendees, agenda, input and output; SDSAP confirms none is missing. | Meeting and reporting map (SDSAP current state) | Planned
C02 | C. Recurring meetings and reports | Do you hold regular calls with each subsidiary? Who joins, what is covered, and which markets need closer contact? | SDSAP COE Lead; market handler | Schedule and content of calls for all 8 markets (including 'no call'). | Subsidiary meeting table | Planned
C03 | C. Recurring meetings and reports | Do you send any daily report? To whom, at what time, what figures does it contain and where do the figures come from? | SDSAP COE Lead | Field list of the daily report, recipients, send time and data source known. | Daily report field list | Planned
C04 | C. Recurring meetings and reports | What goes into the weekly report, who prepares it, by when, and who receives it? | SDSAP COE Lead | Weekly KPI list with definition, source, owner and deadline; BiPlus can rebuild it from Jira. | Weekly report KPI dictionary | Planned
C05 | C. Recurring meetings and reports | How is the monthly/quarterly SLA (composite) calculated and agreed with RHQ? Have there been disputes on the numbers? | SDSAP COE Lead | Calculation and reconciliation process known; risk of gaps between Jira and the report identified. | Note on composite SLA | Planned
C06 | C. Recurring meetings and reports | How does the Monday aging report work, and how do you justify tickets that cannot be cleared within two working days? | SDSAP Merch lead | Aging process and justification template known. | Aging routine | Planned
C07 | C. Recurring meetings and reports | When is the next BVT, and how do you report BVT progress day to day? | SDSAP Tech lead; QA lead | Next BVT date, BVT reporting rhythm and PIC known; BiPlus Leads prepare the PIC matrix. | BVT reporting note | Planned
C08 | C. Recurring meetings and reports | What does an incident report or RCA look like, when is it due and who receives it? | SDSAP COE Lead | RCA structure, deadline and recipients known. | RCA template (structure) | Planned
C09 | C. Recurring meetings and reports | How do you inform RHQ about leave and holiday cover? | SDSAP COE Lead | Channel and frequency for reporting leave known; list of pages BiPlus must take over. | Note on roster / leave | Planned
C10 | C. Recurring meetings and reports | What do RHQ and the subsidiaries ask about most often, and what upsets them most? | SDSAP COE Lead; leads | Top 5 'hot buttons' for RHQ and for subsidiaries, with how to avoid them. | Hot-button list | Planned
C11 | C. Recurring meetings and reports | Where do the report figures come from and how long does it take to prepare each report? | SDSAP COE Lead | Data sources and preparation effort known; request raised to the Atlassian Platform Engineer for automated dashboards. | Reporting dashboard request | Planned
D. Subsidiary (and other party) contacts to watch
D01 | D. Subsidiary (and other party) contacts to watch | For each market, who are the main requesters, who approves at Planning Review, and who is the escalation point? | SDSAP market handlers; BiPlus Merch Sub-Leads | 8/8 markets have at least 1 main requester, 1 approver and 1 escalation contact. | Contact map (stakeholder map) | Planned
D02 | D. Subsidiary (and other party) contacts to watch | Which contacts should we be most careful with, and what works best when dealing with them? | SDSAP COE Lead; market handler | Each 'watch' contact has a reason and a recommended way of working (kept internal to BiPlus). | Notes' column in the contact map | Planned
D03 | D. Subsidiary (and other party) contacts to watch | Besides Oliver and Boon Kiat, who at RHQ do you deal with day to day – reports, BVT notices, access, platform? | SDSAP COE Lead | List of RHQ contacts by function. | Contact map – RHQ | Planned
D04 | D. Subsidiary (and other party) contacts to watch | Who are your contacts at SDS India/Korea, the Spoke BA, global release, the 3PD middleware and Shop App? | SDSAP Tech lead | Contact and channel for each technical party; list of the 4 middleware and the 3PD PIC (open point CM-13 #19). | Contact map – technical parties | Planned
D05 | D. Subsidiary (and other party) contacts to watch | Do you work directly with any partners – payment, NERP, trade-in, logistics? | SDSAP Tech lead | Known which parties interact with the CoE and through which channel. | Contact map – partners | Planned
E. Contact details
E01 | E. Contact details | For each key contact: preferred channel, working hours, expected response time and communication style? | Market handlers; SDSAP COE Lead | At least 80% of key contacts have all 8 information fields. | Contact profiles | Planned
E02 | E. Contact details | Is anyone on the Samsung side about to change role or go on leave? Who covers for them? | SDSAP COE Lead | List of changes and backups. | Backup / changes' column | Planned
E03 | E. Contact details | Are there any open commitments or unresolved issues with subsidiaries or RHQ that we will inherit? | SDSAP COE Lead | List of open commitments, each with a BiPlus owner. | Open commitments list | Planned
E04 | E. Contact details | Which contacts should we be formally introduced to before Sprint 1, and who should make the introduction? | SDSAP COE Lead; RHQ | Introduction plan (who, when, channel) in place before 02/11. | Intro plan | Planned
F. Roles and responsibilities of each contact
F01 | F. Roles and responsibilities of each contact | For each key process, who requests, who approves, who reviews and who must be informed? | SDSAP COE Lead; leads | RACI for 6 processes, exactly one 'A' per process; confirmed by SDSAP. | RACI matrix | Planned
F02 | F. Roles and responsibilities of each contact | Who can decide on priority changes, urgent requests, exceptions or rejecting a request? | SDSAP COE Lead | Decision rights table in place. | Decision rights table | Planned
F03 | F. Roles and responsibilities of each contact | How is your team organised – roles, headcount and what each role does? | SDSAP COE Lead | Role mapping SDSAP ↔ BiPlus, showing roles SDSAP has that BiPlus lacks (and vice versa). | SDSAP–BiPlus role mapping | Planned
F04 | F. Roles and responsibilities of each contact | Where exactly does the subsidiary's responsibility end and the CoE's begin, in practice? | SDSAP Merch lead | List of boundaries and how well they are respected in practice. | Boundary list | Planned
G. Steps from SDM → Lead → member (how SDSAP runs internally)
G01 | G. Steps from SDM → Lead → member (how SDSAP runs internally) | How do you set priorities and targets for your leads each day and week? | SDSAP COE Lead | Rhythm of setting targets from COE lead to leads described. | Cascade note | Planned
G02 | G. Steps from SDM → Lead → member (how SDSAP runs internally) | How do leads split work across members and track individual productivity and quality? | SDSAP Merch/Tech/QA leads | Described for all 3 teams; individual metrics in use identified. | Cascade note per team | Planned
G03 | G. Steps from SDM → Lead → member (how SDSAP runs internally) | What does a typical day look like for you, for a lead and for a team member? | SDSAP COE Lead; leads | Day in the life' for 3 roles, compared with CM-01 §7.2. | Day in the life ×3 | Planned
G04 | G. Steps from SDM → Lead → member (how SDSAP runs internally) | How do you handle backup, leave and onboarding of new people? | SDSAP COE Lead | Actual practice and differences from the BiPlus model known. | Note on backup / onboarding | Planned
G05 | G. Steps from SDM → Lead → member (how SDSAP runs internally) | How do you review quality and share lessons learned inside the team? | SDSAP COE Lead | Internal review rhythm known. | Note on internal quality review | Planned
G06 | G. Steps from SDM → Lead → member (how SDSAP runs internally) | What must a lead report to you immediately? | SDSAP COE Lead | List of internal escalation triggers. | Internal escalation triggers | Planned
H. Agreed working rules (SDSAP ↔ Subs ↔ RHQ)
H01 | H. Agreed working rules (SDSAP ↔ Subs ↔ RHQ) | Are there any agreements – written or unwritten – with each subsidiary on deadlines, cut-offs, support hours or exceptions? | SDSAP COE Lead; market handler | List of agreements per market, marked 'written' or 'unwritten'. | Rules of engagement per market | Planned
H02 | H. Agreed working rules (SDSAP ↔ Subs ↔ RHQ) | What do you use Knox Messenger for with subsidiaries? What would we lose if we could only use Jira comments? | SDSAP COE Lead | List of work going through Knox and the risks; question sent to RHQ on Day 2. | Input to RHQ on the subsidiary channel | Planned
H03 | H. Agreed working rules (SDSAP ↔ Subs ↔ RHQ) | What has been agreed with RHQ on reporting, escalation and approvals? What does RHQ prefer not to be bothered with? | SDSAP COE Lead | List of do's and don'ts with RHQ. | Do's and don'ts with RHQ | Planned
H04 | H. Agreed working rules (SDSAP ↔ Subs ↔ RHQ) | Are there any practices you follow that are not written in RHQ's guidelines? | SDSAP leads | List of practical differences vs CM-13, each with a decision: apply / ask RHQ / drop. | Gap list vs CM-13 | Planned
H05 | H. Agreed working rules (SDSAP ↔ Subs ↔ RHQ) | In practice, how do you handle: ON HOLD ES, L.V. Approval, publishing before or after Review Setup, waiting for Knox, and calendar vs working hours for Medium/Low SLAs? | SDSAP COE Lead; leads | Each point marked 'clear from practice' or 'needs RHQ answer'; next CM-13 version updated. | Updated CM-13 open points table | Planned
I. Tools, dashboards, channels
I01 | I. Tools, dashboards, channels | Which system access do you have that we may still be missing? | SDSAP Tech lead | Access gap list and the AUTEU tickets to raise. | Access gap list | Planned

## Quytd
Master plan: Quytd - Technical
Main objectives | What the Tech side must come back with
Objective 1 | See how SDSAP runs Tech work on real tickets from start to end: intake, configuration and production change, escalation, on-call. Why: BiPlus runs this work after take-over, so it has to be seen, not read. Evidence: Observed flow for each ticket type, with the tickets used as examples.
Objective 2 | Compare what is seen with the BiPlus documents (TC-01 to TC-05, TEC runbooks) and mark every difference. Why: The documents were written from papers; the visit is the one chance to test them against live work. Evidence: Gap list against the documents, each gap with an owner.
Objective 3 | Close the items still marked proposal or to be confirmed. Why: Open items today include PC rules, SLA start point, on-call after hours, 3PD ownership, healthcheck thresholds and BVT roles. Evidence: Each open item answered, or recorded as not available with a reason.
Objective 4 | Collect the working material Tech needs: templates, runbooks, contacts, tools, access routes. Why: Without it, BiPlus cannot take the load in Sprint 1. Evidence: Collection list (sheet Quytd Collect) fully marked.
Objective 5 | Prepare a Tech load proposal for the four sprints and agree it in the November plan meeting. Why: The ramp-up is 10, 30, 60 and 90 percent, with the first 24/7 week in Sprint 3 and Black Friday in Sprint 4. Evidence: One-page proposal; Tech part of the meeting note.
Objective 6 | Leave with named contacts and an agreed way to ask short questions until 30 November. Why: Questions will come up after the visit. Evidence: Contact named for Tech.
Day | Time | Main activity | BiPlus does | SDSAP does | RHQ does | Done when | Questions to ask | Information to collect | Status
Before the visit | Goal: Agree access, schedule and baseline data first, so the four days are not spent on setup.
| Before departure | Agree the plan | Send the visit lead the changes needed to the master plan: Tech added to Peak days and to Backlog and tools; a fallback for Tech situations that may not occur during the week; named Tech counterparts; the dates. | Name the Tech Lead and Sub-Lead counterparts. | None. | Visit lead has confirmed the changes. |  |  | Planned
| Before departure | Ask SDSAP in advance | Ask for: deployments and PC planned for the week; RHQ calls planned; a list of 5 to 10 recently closed Tech tickets (order issue, integration, escalation, account) to reopen if nothing happens live; permission to view screens and logs and to keep masked screenshots and notes. | Share the list and say what may be shown. | Confirms what BiPlus may see and keep. | Answers received or open points listed. |  |  | Planned
| Before departure | Baseline data | Export the Tech tickets from Jira (volume, type, priority, status, SLA). Reread the BiPlus Tech documents (TC-01 to TC-05 and the TEC runbooks) so gaps can be marked on the spot. | Provide the export if BiPlus cannot reach it. | None. | Baseline ready for the load proposal. |  |  | Planned
Day 1 | Goal: See how Tech work arrives, is triaged and is changed in production: intake, queue, configuration requests, PC tickets, healthcheck and shift handoff. (Master plan Day 1 brief + Day 2)
| 09:30 to 10:00 | Welcome and ground rules | Tech Lead and Sub-Lead meet the SDSAP Tech counterparts: site and data rules, pairs. Ask for permission to sit in on escalations, view the on-call log and listen to RHQ calls. | Short welcome; introduce the counterparts; say what may be viewed and copied. | None. | Pairs agreed; permissions noted. | 1. What may BiPlus view, copy or photograph, and may BiPlus sit in on escalations and listen to RHQ calls? | - Names of the Tech counterparts - Notes on permissions | Planned
| 10:00 to 12:30 | Intake, queue and operations | Sit beside the person who triages Tech tickets: where tickets come from, priority P0 to P4, who assigns, Level 1 and Level 2, the split between Team A and Team B. Join the Service Delivery Manager for SLA monitoring, tickets waiting on Samsung L2/L3 and PC and Knox approvals. | Work as normal. Available online for questions BiPlus should not take to SDSAP. |  | Intake flow confirmed from arrival to assignment; PC approval chain seen. | 1. Where do Tech tickets come from, who sets P0 to P4, and who may change a priority? 2. How are tickets assigned and split between Team A and Team B, how do Level 1 and Level 2 differ, and does the SLA start at NEW or at ASSIGNED? | - Intake flow from arrival to assignment - Definition of P0 to P4 and who may change a priority - Assignment table, and the Team A and Team B split (VN, TH, ID, NZ and SG, MY, PH, AU) - Difference between Level 1 and Level 2 work - Where the SLA clock starts and stops | Planned
| 13:00 to 15:30 | Configuration requests and PC tickets | Follow 2 to 3 real tickets through the whole cycle: review, PC, waiting for RHQ approval, run, launch verification. Note the PC template and mandatory fields, the second check, the ImpEx header, rollback and the waiting time for approval. | Work as normal; let BiPlus sit beside the person making the change. |  | 2 to 3 tickets followed; one masked PC example collected. | 1. Can several tickets go into one PC ticket, which fields are mandatory, how long does RHQ approval take, and what is done when it is urgent? 2. How are the second check, the ImpEx header and the rollback done? 3. Which configuration requests does Tech do alone, and which need Samsung L2/L3? | - One real PC ticket, masked - List of mandatory PC fields - Typical waiting time for RHQ approval and the urgent route - Second-check checklist - ImpEx header sample and rollback steps - List of configuration requests: done by Tech alone, or with Samsung L2/L3 - Rule on one PC for several tickets | Planned
| 15:30 to 16:30 | Healthcheck and shift handoff | Observe how orders are monitored (HAC, Kibana, reports to subsidiaries) and how the day is handed over to the next shift. | Work as normal. |  | Healthcheck and handoff routine written down. | 1. How are orders monitored and reported to the subsidiaries (HAC, Kibana), and what is in the end-of-day handoff? | - Daily healthcheck routine, tools used and report sent - End-of-day handoff template | Planned
| 16:30 to 17:00 | Read-back | Read the day notes back to the SDSAP counterpart. List the gaps against the BiPlus documents. | Confirm or correct the notes. |  | Notes confirmed; gap list started. |  | - Gap list against TC-01 to TC-05 and the TEC runbooks | Planned
Day 2 | Goal: See the harder Tech situations: order issues, integrations, escalation to Samsung L2/L3, account requests, and, if they occur, incidents and tests. (Master plan Day 3)
| 09:30 to 11:30 | Order issues | Observe how a stuck order is diagnosed (order process, task log, Kibana logs), which step is rerun, and the job and step names used on this site. If no order issue occurs, reopen 2 to 3 closed order tickets and walk through them. | Work as normal; call BiPlus over when an order issue comes in. | None. | Diagnosis and rerun steps seen on live or reopened tickets. | 1. How is a stuck order diagnosed and rerun, and what are the job and step names on this site? 2. Which failures can Tech fix alone, and which go to Samsung? What do the clawback statuses and the fraud threshold mean? | - Diagnosis steps for a stuck order - List of jobs and steps rerun, with site names - List of order failures: fix alone or send to Samsung - Meaning of clawback statuses and the fraud threshold | Planned
| 11:30 to 12:30 | Integrations and 3PD | Sit with the 3PD person in charge: middleware, ERP, payment gateway, trade-in partner. For each type of error: who fixes it. | Work as normal. |  | Integration points and the owner of each error type listed. | 1. Which middleware are in use, who is the 3PD person in charge, and who fixes each type of error? 2. How often does the sync run, and which Jira project and SLA apply to 3PD? | - Integration map with the owner of each error type - Name of the 3PD person in charge, Jira project and SLA for 3PD - Sync schedule | Planned
| 13:30 to 15:00 | Escalation to Samsung L2/L3 | Observe a Maintenance Request: evidence pack, follow-up rhythm, the backlog of system support tickets, how the Spoke is used. If none occurs, reopen 2 past escalations. | Let BiPlus sit in on escalations. |  | Escalation path drawn from real tickets. | 1. What must a Maintenance Request contain (evidence pack)? 2. How often is it followed up, and how long does SDS India take to reply in practice? | - One Maintenance Request with its evidence pack, masked - Escalation contacts and follow-up rhythm - Snapshot of the system support backlog (count and age) | Planned
| 15:00 to 15:30 | Account requests | Observe access requests: back-office password reset, IP whitelist, access to the 3PD middleware, and who approves each. | Work as normal. |  | Account request routes and approvers noted. | 1. How are password resets, IP whitelist requests and middleware access handled, and who approves each? | - Account request routes and approvers | Planned
| 09:30 to 17:00 | Incidents, on-call, RHQ calls and tests (if they occur) | Sit in on incidents and on-call handling: call tree, how Critical issues are reported to RHQ, how after-hours is handled. Listen only to RHQ or subsidiary calls. Sit in on a BVT or sanity test if one runs this week. | Let BiPlus listen in where suitable; agrees that BiPlus may listen to RHQ calls this week. |  | Observed if they occur; otherwise recorded as Not seen. | 1. What is the call tree, how is a Critical issue reported to RHQ, how are out-of-hours tickets handled, how long does P0 really take, and who is on call? 2. Who is the BVT Coordinator, and does the 16:30 deadline apply to Tech? | - Call tree and the Critical notice to RHQ - Out-of-hours rule for P2 to P4 and the real response time for P0 - On-call roster and log format - BVT coordinator, deadline, and the Tech part of a BVT or sanity test | Planned
| 16:30 to 17:00 | Read-back | Read the day notes back to the SDSAP counterpart. | Confirm or correct the notes. |  | Escalation map and integration owners confirmed. |  | - Confirmed escalation map and integration owner list | Planned
Day 3 | Goal: See open work per market, how the backlog is reviewed, and how Tech prepares for the peak days. (Master plan Day 4)
| 09:30 to 11:00 | Backlog and tools | With the Service Delivery Manager, see how the backlog is reviewed and the tools used every day: Jira queries and filters, dashboards, chat channels, Kibana clusters, HAC environments, staging accounts. | Work as normal. | None. | Backlog routine and tool list written down. | 1. How is the backlog reviewed: who, how often, with which filters? 2. Which filters, dashboards, chat channels, Kibana clusters, HAC environments and staging accounts are used every day? | - Backlog review routine - List of Jira queries and filters, dashboards, chat channels - Kibana clusters, HAC environments, staging accounts | Planned
| 11:00 to 12:30 | Open Tech work: Team A (VN, TH, ID, NZ) | Go through open tickets, system support tickets, tickets on hold waiting for RHQ and PC tickets waiting. Tag each kind of work by the sprint in which BiPlus takes it (S1 to S4) or SDSAP keeps it. Note what is different in each market. |  |  | Pending work seen for Team A markets. | 1. For each kind of open work: can BiPlus take it in Sprint 1, 2, 3 or 4, or should SDSAP keep it? 2. What is different in each market, and what is waiting for RHQ and for how long? | - Open Tech work per market, each kind tagged Sprint 1 to 4 or kept by SDSAP - What is different in each market | Planned
| 13:30 to 15:00 | Open Tech work: Team B (SG, MY, PH, AU) | Same as the morning for the Team B markets. |  |  | Pending work seen for Team B markets; table per market started. | 1. Same questions as for Team A, for the Team B markets. | - Same as Team A: the table of open work per market, tagged by sprint, and the differences between markets. | Planned
| 15:00 to 16:00 | Peak days: 11.11, Black Friday, Cyber Monday | Observe freeze window, PC timeline before and after the peak, healthcheck frequency, enhancements and releases planned for November, who is on duty. (Tech is not named in this master plan line: confirm with the visit lead.) | Work as normal; share the peak calendar. |  | Peak checklist and duty roster seen. | 1. When is the freeze window, what is the PC timeline from T-14 to T+1, and which healthcheck checks (HC-01 to HC-08), thresholds and run times apply? 2. Which enhancements, releases and BVT are planned in November, and who is on duty on the peak days? | - Healthcheck list HC-01 to HC-08 with thresholds and times - Freeze window, PC timeline T-14 to T+1 - November enhancements, releases and BVT - Duty roster for 11.11, Black Friday and Cyber Monday | Planned
| 16:00 to 17:00 | Draft load proposal and read-back | Draft the Tech load proposal for Sprints 1 to 4 (sheet Quytd Load). Read the day notes back to the SDSAP counterpart. | Confirm or correct the notes. |  | Open work per market tagged; first draft of the proposal. | 1. Which notes of the day are wrong or incomplete? | - First draft of the Tech load proposal (see the table at the bottom of this sheet) | Planned
Day 4 | Goal: Fill in what has not been seen; agree the November plan; close the visit. (Master plan Day 5)
| 09:30 to 12:30 | Situations not seen yet | Go through the collection list (sheet Quytd Collect) with the SDSAP Tech Lead: observe what is still missing, read back all notes, close open items. | Work as normal; answer open items. | None. | Every item on the list is marked collected or not available, with a reason. | 1. What has not been seen yet, and can it be shown today? | - Documents still missing from the week | Planned
| 12:30 to 14:00 | Finish the Tech proposal | With the BiPlus visit lead, finish the one-page Tech proposal for the meeting. | Work as normal. |  | One-page proposal ready. |  |  | Planned
| 14:00 to 15:30 | November plan: overlap and load ramp-up | Share what was observed. Propose the Tech load for each of the four sprints, the on-call handover, and who covers 11.11, Black Friday and Cyber Monday. | Confirms the work it keeps in each sprint, how it reviews BiPlus work during the overlap, and who covers the peak days. | Chairs the meeting. Agrees the load share, the SLA owner in each sprint and the sprint rhythm. | Tech load, SLA owner and on-call for Sprints 1 to 4 written in the meeting note. | 1. What load can BiPlus take in each sprint, and what does SDSAP keep? 2. How will SDSAP review BiPlus work in the overlap, and who holds the SLA in each sprint? 3. Is the on-call handover agreed (SDSAP in Sprint 1, BiPlus for handed-over tickets in Sprint 2, 24/7 from Sprint 3), and who covers 11.11, Black Friday and Cyber Monday? 4. Should bulk fixes with ImpEx or Groovy, escalation to SDS India and BVT PIC start in Sprint 4, the Black Friday week? | - Agreed Tech load per sprint, SLA owner and on-call handover, from the meeting note | Planned
| 15:30 to 16:30 | Thank-you and wrap-up | Ask for one Tech contact for short questions until 30 November, and for any documents still missing. | Name contacts, if willing. | Receives a short observation summary after the visit. | Contact named; visit closed. | 1. Who is the Tech contact until 30 November, and how is that person reached? | - Named Tech contact until 30 November | Planned
After the visit | Goal: Use what was observed; take over the Tech load sprint by sprint.
| To 30 November | Follow-up | Send the Tech part of the observation summary to the visit lead for RHQ within one working day. Update TC-01 to TC-05 and the TEC runbooks and close the items marked to be confirmed. Turn the real cases into practice scenarios for the staging back office. | Answer short questions if contacted. | Forward questions to SDSAP if needed. | Documents updated; observations used in Academy training and Sprint 1. |  |  | Planned
| End of each sprint (Sprints 1 to 4) | Sprint retrospective and plan | Present the Tech results (work taken over, SLA, quality, issues), the improvements and the proposed load for the next sprint. | Gives feedback on BiPlus work and confirms what it hands over next. | Chairs the meeting. Agrees improvements and the load share for the next sprint. | Next sprint plan agreed; every improvement has an owner. |  |  | Planned

## TungNS
MALAYSIA OPS COE VISIT - PERSONAL WORKING PLAN
TungNS - Merchandising Team (covering all Merchandising roles) - Malaysia & Thailand Markets
Executive Summary: On-site operational observation at Malaysia Ops COE to map current merchandising workflows, shadow system touchpoints, document market nuances for MY & TH
Obj # | Objective Domain | Target Outcome & Shadowing Goal
OBJ-01 | End-to-End Workflow Mapping | Trace campaign lifecycle from subsidiary marketing brief submission to final live store publishing.
OBJ-02 | Tool Ecosystem Deep Dive | Hands-on observation of Hybris Backoffice, Adobe Experience Manager (AEM), Jira workflows, and catalog feeds.
OBJ-03 | Market Localization & Language Rules | Document bilingual rules for Thailand (Thai/English RHQ notes) and specific formatting standards for the Philippines.
OBJ-04 | Pre-Staging & Cutoff Governance | Determine strict submission deadlines, staging freeze windows, and SLA tiering for flash and mega campaigns.
OBJ-05 | Cross-Functional Approvals & QA | Map handoff chains between Merchandising leads, QA specialists, Tech Teams A/B, and Subsidiary Brand PICs.
OBJ-06 | Bottleneck & Rollback Identification | Catalog standard troubleshooting protocols, failed promotion rollback procedures, and emergency patch channels.
Question ID | Theme / Operational Domain | Survey Question & Operational Exploration | Priority | Status | Field Notes & Key Observations
A-01 | A. Campaign Intake & Briefing Process | How are late brief submissions or last-minute scope changes handled, and who has approval authority? | Medium | Not Started
A-02 | A. Campaign Intake & Briefing Process | How are conflicting priorities between regional HQ campaigns and local subsidiary campaigns resolved? | Medium | Not Started
B-01 | B. Catalog Management & Product Master Data | What attributes are mandatory for PH vs TH site search and faceted navigation filters? | Medium | Not Started
B-07 | B. Catalog Management & Product Master Data | How are product badges (e.g., 'New', 'Best Seller', 'Online Exclusive') assigned and scheduled? | Low | Not Started
B-08 | B. Catalog Management & Product Master Data | What is the protocol when an SKU has discontinued status or zero inventory during a live campaign? | Medium | Not Started
D-03 | D. Promotion Engine & Voucher Logic | How are minimum spend thresholds, maximum discount caps, and usage limits (per customer / total) enforced? | High | Not Started
D-06 | D. Promotion Engine & Voucher Logic | What prevents voucher abuse or exploit leakage during high-velocity mega sales? | High | Not Started
E-07 | E. Bundling, GWP & Add-on Deals | What are the primary failure points observed in bundle discount calculations during peak traffic? | High | Not Started
F-01 | F. Content Management & AEM Landing Pages | What is the standard template architecture and component library used in AEM for promo landing pages? | High | Not Started
F-02 | F. Content Management & AEM Landing Pages | How are responsive banners (desktop vs mobile viewport) cropped, optimized, and published? | High | Not Started
F-03 | F. Content Management & AEM Landing Pages | How are dynamic countdown timer components configured and synced with midnight campaign launches? | High | Not Started
G-01 | G. Market Localization & Language Rules | What is the step-by-step translation and review process for Thai language content and campaign banners? | High | Not Started
G-02 | G. Market Localization & Language Rules | How are English summary notes structured and filed for regional HQ (RHQ) oversight on Thai campaigns? | High | Not Started
G-03 | G. Market Localization & Language Rules | What specific legal disclaimers, T&Cs, and regulatory notices are mandatory for PH vs TH promotions? | High | Not Started
G-04 | G. Market Localization & Language Rules | Who performs the native Thai language linguistic and cultural QA before pages go live? | High | Not Started
G-05 | G. Market Localization & Language Rules | How are localized character encodings, fonts, and text expansion accommodated on responsive layouts? | Medium | Not Started
G-06 | G. Market Localization & Language Rules | How do communication channels differ between site's teams? | Medium | Not Started
G-07 | G. Market Localization & Language Rules | Are there specific cultural calendar events (e.g., Songkran in TH, Ber months in PH) with unique rules? | Medium | Not Started
H-01 | H. QA & Staging Verification | What sandbox / staging environments exist for PH and TH, and how closely do they mirror production? | High | Not Started
H-03 | H. QA & Staging Verification | How are end-to-end test orders placed without triggering live payment gateway charges or real inventory holds? | High | Not Started
I-04 | I. Go-Live Procedures & Peak Shifts | What real-time communication war room channels (Teams, Slack, Google Chat) are activated during peak launches? | Medium | Not Started
I-06 | I. Go-Live Procedures & Peak Shifts | How are cache-clearing and CDN purge requests triggered if landing page updates do not display immediately? | Medium | Not Started
J-02 | J. Emergency Fixes & Rollbacks | What is the step-by-step rollback procedure if a promotion causes unintended extreme discounts? | High | Not Started
J-03 | J. Emergency Fixes & Rollbacks | How quickly can an emergency banner swap or price correction be deployed to production? | High | Not Started
J-06 | J. Emergency Fixes & Rollbacks | How are orders placed under an unintended glitch price handled from an operations and legal standpoint? | Medium | Not Started
K-03 | K. Governance & Team Handoffs | What regular sync meetings (daily standups, weekly campaign reviews) are held with subsidiary marketing PICs? | Medium | Not Started
K-04 | K. Governance & Team Handoffs | How are change requests during active campaigns documented and formally approved? | High | Not Started
L-01 | L. Readiness & Transition Risks | What are the most frequent system slowdowns or technical pain points experienced in daily Backoffice use? | High | Not Started
L-02 | L. Readiness & Transition Risks | Which repetitive tasks consume the highest manual operator hours? | High | Not Started
L-04 | L. Readiness & Transition Risks | How will shadow ticketing and dual-running be supervised by SDSAP during November ramp-up? | High | Not Started
SERVICE FOCUS PLAN - sessions for TungNS's Tier 1 services (from the BiPlus visit brief 26 Oct; Service Pack summaries in D:\coe-doc\SDSAP\tung-handover)
Own services (PIC = Tùng, Owner): MER-AEM-04, MER-AEM-01, MER-PRC-01, MER-PRC-02, MER-SAC-01, MER-PRF-04, MER-PRM-06. Part C (PIC = Tung): TEC-ORD-07, TEC-ORD-02/03 - not Tier 1 owner. Times are Kuala Lumpur time.
Day / time / room | Session (SDSAP handover) | Service and Service Pack (BiPlus Wiki) | Priority | Status | Prepare / ask / field notes
Day 1 - Tue 27 Oct 10:10 Room A | Topic 11: Add-on Page with AEM additional info (SDSAP: Ong Hee Hui) - verdict Reuse | MER-PRF-04 Must purchase with (freebie) reference setup Tier 1 #27, Optional, Sprint 4 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483598148 | Medium | Not Started | A normal freebie = free-gift PROMOTION RULE, not a reference; MUST_PURCHASE_WITH only for a mandatory companion (e.g. AC indoor+outdoor). Ask how gift is set on the add-on / gift-selection page vs a rule; gift readiness (Z-Code PURCHASABLE_NOT_VISIBLE/Approved, price 0, stock source). Prep: Service Pack sec. 1-2.1.
Day 1 - Tue 27 Oct 10:50 Room A | Topic 15: Knox Approval (SDSAP: Chong Haw Eong) - verdict Reuse | MER-PRC-02 Special price setup Tier 1 #11, Must, Sprint 3 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483598300 | High | Not Started | Knox side of special price: path follows highest discount in the submit, max 300 rows/submit, submit same working day, chase at 50% SLA / go-live-1 day / -4h; approver on leave (APE017), KNOXREJECTED; does SLA clock stop while waiting (it does not in the pack). Prep: Knox Approval KB 2477982196.
Day 1 - Tue 27 Oct 11:05 Room A | Topic 16: Overtrade (SDSAP: Ong Hee Hui) - verdict Clarify (NZ only page) | MER-PRM-06 Overtrade (trade-in) promotion Tier 1 #30, Optional, Sprint 4 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483696835 | Medium | Not Started | Mechanism first: M1 discount configuration (TRADE_IN AddedServiceConfig / TRADE_IN_DEVICE_PRICE upload) vs M2 CE trade-up (MSA) vs M3 rule-based bonus (Knox). A discount config has NO publish state - future Start Date / Open discount=false; never delete, end it. Ask how it works in MY/ID/PH/TH/SG/AU and how QA tests before start date; who confirms the amount table with the partner.
Day 1 - Tue 27 Oct 10:30 Room B (Tech) overlaps 10:10-10:50 Room A | Topic 22: Order processes E2E (SDSAP: Aldwin John Gavino) - Clarify - Part C #8 'Order cancellation and return' asked inside | TEC-ORD-02 Order cancellation (Tier 1 #21) + TEC-ORD-03 Order return (#23) Must, Sprint 4 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483728928 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483631394 | Medium | Not Started | Not in the SDSAP inventory (Part C). Room B clashes with Room A: send the Tech person or use the recording. Get Hybris->NERP flow with statuses, CS cockpit cancel steps, refund method per market, three-system check (Hybris/NERP/gateway), return reset (Order Remediation case 3) and TH 'unable to create return' list. No rollback after cancel/refund.
Day 1 - Tue 27 Oct 17:00-22:00 | Evening: update Service Packs (Thao's review) | MER-PRF-04, MER-PRC-02, MER-PRM-06 | Medium | Not Started | Write comments on the three BiPlus Wiki pages from today's sessions; set Verify status/Verdict; list open questions for Quoc.
Day 2 - Wed 28 Oct 14:45 Room A | Part C #4: Shop App content management (added session - no SDSAP page) | MER-SAC-01 Shop App content management Tier 1 #26, Optional, Sprint 4 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483631521 | Medium | Not Started | Ownership matrix B2C Home (not COE-editable) / Offer / Shop / EPP; approval chain ASC -> Suwon Office, 24h go-live rule; weekly AU offer rotation; daily QA triage A-D (TH, AU); content rules (no numbers in head copy, no 'Buy now'). Ask for session AND KB page. Check access now: CMS role, IP whitelist (AUTEU), OTP.
Day 2 - Wed 28 Oct 17:00-22:00 | Evening: update Service Pack | MER-SAC-01 | Medium | Not Started | Update the Shop App page; record ASC_Operation QA Request SLA table (confirm in KT) and the min offer KV count.
Day 3 - Thu 29 Oct 10:00 Room A | Topic 43: Price Row (SDSAP: Ong Hee Hui) - verdict ADD, no link | MER-PRC-01 Price upload Tier 1 #8, Must, Sprint 2 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483631159 | High | Not Started | No SDSAP page: record the session so BiPlus writes the guide. Capture real steps vs runbook (SPECIAL_PRICE template for RRP/regular? block-price flag, Knox route, sync, Check B). Resolve KT points: may Merch run Knox cronjob manually, periodicPriceCleanupCronJob scope, upload during hard freeze. UTC table: SG/MY/PH 16:00 prev day; TH/VN/ID 17:00.
Day 3 - Thu 29 Oct 11:20 Room B (Tech) overlaps 11:30 Room A | Topic 56: FI Posting (SDSAP: Mohammad Ashhar Mushtaq) - Reuse - Part C #7 'Invoice and e-invoice' asked inside | TEC-ORD-07 Invoice and e-invoice generation and correction Tier 1 #14, Must, Sprint 3 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483729047 | Medium | Not Started | Not in inventory. KB has nothing on the daily MY batch or MY e-invoice flow: who submits, what returns, role of revalidation jobs; does Completed trigger invoice generation; approved push action; batch limit (50); standing PC for routine MY batches. Production rights by wave from 29 Oct.
Day 3 - Thu 29 Oct 11:30 Room A | Topic 44: Discount Row (SDSAP: Ong Hee Hui) - verdict ADD, no link | MER-PRC-02 Special price setup (also maps to MER-PRC-03) Tier 1 #11, Must, Sprint 3 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483598300 | High | Not Started | Boundary: discount row vs special price vs promotion; a discount row cannot hold same SKU with different validity ('duplicated PriceInfoChange'). Overlap + stacking checks, Check B at start / Check C at end, AON resume after window (SEAU says yes, tickets show RRP).
Day 3 - Thu 29 Oct 14:15 Room A | Follow-up of topics 6-8 (26 Oct): Topic 8 Z-code, F-code Setup - verdict Clarify | MER-PRF-04 Must purchase with (freebie) reference setup Tier 1 #27, Optional, Sprint 4 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483598148 | Medium | Not Started | KB covers Z-code standardisation only: which page covers F-code bundles (virtual + hard bundle)? Gift readiness end to end; MUST_PURCHASE_WITH vs CONSISTS_OF; bulk upload PRODUCT_REFERENCES.
Day 3 - Thu 29 Oct 17:00-22:00 | Evening: update Service Packs | MER-PRC-01, MER-PRC-02, MER-PRF-04, TEC-ORD-07 | Medium | Not Started | Pack comments; mark Verify status; list what SDSAP did not hand over (Price Row / Discount Row have no page).
Day 4 - Fri 30 Oct 10:00 Room A | Topic 61: EPP CMS - Country EPP structure - All AEM component (SDSAP: Siti Sarah / Thananya) - verdict Reuse | MER-AEM-01 AEM page creation and update (Homepage, PF, FAQ, Footer) Tier 1 #4, Must, Sprint 1 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483598824 | High | Not Started | Walk component limits live (HD01 headline 30 / description 78, PD10 max 12 cards, image sizes) and the per-country component sheet. KT points: AEM server time zone, versioning in EPP 2.0 CMS, scheduled publication, cache purge, who approves before PRD SETUP, boundary with MER-AEM-04. Ayu covers on site for Geraldus.
Day 4 - Fri 30 Oct 10:20 Room A | Part C #1: Campaign page and banner setup on AEM (added session - no SDSAP page) | MER-AEM-04 Campaign page and banner setup Tier 1 #2, Must, Sprint 1 https://biplus.atlassian.net/wiki/spaces/SamsungCoETech/pages/2483697164 | High | Not Started | Daily request type (ID, VN > half). Ask session AND KB page: banner matrix, internal/external EPP variants, go-live sequencing with the offer behind the banner, removal sub-task, EPP 2.0 CMS vs AEM author, AEM QA access via QA Auth (~24h), AEM-disabled / RHQ-run sites, LastMinRequest rule.
Day 4 - Fri 30 Oct 14:00 (30 Oct) | November plan agreement (RHQ + SDSAP) | Tùng's sprint services: S1 MER-AEM-04, MER-AEM-01 ¦ S2 MER-PRC-01 ¦ S3 MER-PRC-02 ¦ S4 MER-SAC-01, MER-PRF-04, MER-PRM-06 | High | Not Started | Confirm the services per sprint, how they are routed in Jira and who holds the SLA. Note: Sprint 1 has no price/discount service; prices and vouchers from Sprint 2; SDSAP keeps 11.11 campaign changes.
Unscheduled | Topic 3: Standard Template (follow-up in Q&A, no slot) | MER-PRC-01 + MER-PRC-02 (also MER-PRM-01) | Low | Not Started | Is this the version all 8 markets use? Which request type needs which template? Any encrypted file left (RHQ sent decrypted templates 22 Oct)?
Additional questions from the Service Packs (same format as the survey above)
Question ID | Theme / Operational Domain | Survey Question & Operational Exploration | Priority | Status | Field Notes & Key Observations
S-01 | S. Service focus: MER-PRC-01 Price upload | Is the Special Price template (SPECIAL_PRICE) really used for regular/RRP price rows, and who uses the block-price flag (blockPriceUpdatesFromExternalSystems) before an RRP change? | High | Not Started
S-02 | S. Service focus: MER-PRC-01 Price upload | Can Merch run knoxPriceApplyingJob by hand when records stay KNOXAPPROVED, and what is the scope of periodicPriceCleanupCronJob (unsubmitted records removed at 23:00)? | High | Not Started
S-03 | S. Service focus: MER-PRC-02 Special price | How do you detect and prevent overlap between price windows and stacking with active promotions before upload (Check A)? Who does Check B at start and Check C at end, especially out of hours? | High | Not Started
S-04 | S. Service focus: MER-PRC-02 Special price | After a special price ends, does the Always-On price resume or does RRP show (SEAU page vs ticket evidence)? What is a VN 'single price setting' exactly? | High | Not Started
S-05 | S. Service focus: MER-PRC-02 Knox | Who are the Knox approvers per path and per market, how long do approvals take, and what happens on APE017 (approver on leave) or KNOXREJECTED? Does the SLA clock stop while waiting? | High | Not Started
S-06 | S. Service focus: MER-PRM-06 Overtrade | Which mechanism does each market use (discount configuration vs promotion rule vs CE trade-up in MSA), and how is a config tested before its Start Date given it has no publish state? | Medium | Not Started
S-07 | S. Service focus: MER-PRM-06 Overtrade | Who confirms the amount table with the trade-in partner, how is that confirmation recorded, and how is the end of the window verified (AU/NZ midnight = VN evening)? | Medium | Not Started
S-08 | S. Service focus: MER-PRF-04 Freebie | Which promotion template is the standard for a plain FOC per market, and what are the rule group/priority values (VN 600 vs 150/999 on staging)? When do you use MUST_PURCHASE_WITH instead of a rule? | Medium | Not Started
S-09 | S. Service focus: MER-PRF-04 Freebie | When extending a gift, how do you make sure every channel copy (B2C, O2O, EPP groups, SMB, EA) is changed, and how is gift readiness (Z-Code status, price 0, stock source) checked? | Medium | Not Started
S-10 | S. Service focus: MER-AEM-04 Banners | How is the banner matrix built per site group, how are EPP 2.0 CMS vs AEM author pages distinguished, and what is the removal practice at campaign end? | High | Not Started
S-11 | S. Service focus: MER-AEM-01 Pages | AEM server time zone, versioning in EPP 2.0 CMS, scheduled publication/unpublication and cache purge: what is the real procedure, and who approves before PRD SETUP? | High | Not Started
S-12 | S. Service focus: MER-AEM-01 / AEM-04 | Where is the boundary between MER-AEM-01 (homepage tiles) and MER-AEM-04 (hero/merch banners) in practice, and how do QA sampling (AEM-04) and peer check (AEM-01) work today? | Medium | Not Started
S-13 | S. Service focus: MER-SAC-01 Shop App | Who edits B2C Home vs Offer vs Shop vs EPP, how does the ASC -> Suwon Office approval work in practice, and what are the SLA and ownership rules for ASC_Operation QA Request (daily QA findings)? | Medium | Not Started
S-14 | S. Service focus: MER-SAC-01 Shop App | How are weekly offer rotations scheduled (minimum KV count, ending the previous week at the new start), and how are AOS/iOS tested without a Samsung device? | Medium | Not Started
S-15 | S. Service focus: Tech (Part C) TEC-ORD-02/03/07 | Order cancel/return: which NERP-side confirmations are needed, how is the TH 'unable to create return' list reset, and when is a refund triggered (on goods receipt)? Invoice: who submits the MY e-invoice and does Completed trigger invoice generation? | Medium | Not Started

## Ayu
Merch-Sub Lead Indonesia
Day | Time | Main activity | BiPlus does | Question | Outcome
Day 1 | Goal: See how the COE runs: intake, triage, assignment and the daily rhythm.
| 09:30 to 15:30 | Markets | Merchandising Sub-Leads sit beside the person who handles each market: live queue, requesters, channels, language. | 1. How the baseline metrics, such us: a. Turnaround times (TAT) for product listings, order processing, and ticket resolutions. b. Inventory & Quality Metrics: Catalog accuracy rates, out-of-stock (OOS) frequencies, and return/refund percentages due to merchandising errors. c. Shrinkage & Productivity: Team utilization rates, average handling time (AHT) for merchandise updates, and daily throughput expectations. (if any) d. Team roster & skill matrix, roster details, skill matrix, corss training
Day 2 | Goal: See the main request types done on live tickets.
| 09:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe product, price, promotion, voucher and stock setup for each market, and the checks before QA. | 2. Workflows • Product Lifecycle Management: The exact workflow from receiving raw subs data/images • Pricing & Promotions: Is there any approval matrix and execution steps for markdowns, flash sales, and coupon codes. • QA Collaboration: The process cross team collaboration among Merch and QA • Access Matrix: Is there any list as read-only vs. administrative rights on the client’s live systems. 3. Subs Management: How you manage the subsidiaries contact. 4. Im
Day 3 | Goal: See the harder situations: urgent requests, escalations, launches.
| 09:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe urgent requests, bulk updates, AEM and Shop App content, and EPP, SMB, O2O and 3PD store requests. | - Is there any tier level to prioritize the bulk request/update. Eg, priorities Shop App then SMB...
Day 4 | Goal: See open work and how each market differs.
| 09:30 to 15:30 | Open work per market | Merchandising Sub-Leads observe open tickets and pending work for each market. Tech Lead and Tech Sub-Lead observe open Tech work by market. | - How is the interface the open tickets?
| 09:30 to 17:00 | Peak days | Merchandising and QA observe preparation for 11.11, Black Friday and Cyber Monday, and any launch this week. | - How many days do we need at least, to prepare the Black Friday /Cyber Monday / Launch this week?
Day 5 | Goal: Fill in situations not seen yet; agree the November plan; close the visit.
| 09:30 to 12:30 | Situations not seen yet | Each BiPlus person observes the situations not yet seen during the week.
| 14:00 to 15:30 | November plan: overlap and load ramp-up | BiPlus visit lead and the team Leads share what was observed and propose the load BiPlus takes in each of the four sprints, per team (Merchandising, Tech, QA), starting from the RHQ transition plan.
| 15:30 to 16:30 | Thank-you and wrap-up | BiPlus visit lead thanks SDSAP and asks for one contact per team for short questions until 30 November.
| To 30 November | Follow-up | Send a short observation summary to RHQ within one working day. Turn notes into BiPlus runbooks and training.

## Thanhvd
Master plan: Thanhvd - SubLead Merchandise
Ngày | Objective | Question to SDSAP team | Output
Day 1 | Observe COE Operations: - Intake, triage, assignment, and daily rhythm. - Live queue management, channels, and languages (specifically VN and AU). | 1. How does the system or team prioritize (triage) incoming tickets from multiple channels during high-traffic hours? 2. Are tickets assigned manually by a lead, or do Merchandisers actively pull them from the live queue based on specific rules? 3. What are the most common challenges or specific local nuances when handling requests for the VN and AU markets? 4. How do you handle ambiguous instructions from local market requesters? 5. How do you hand over between shift? | 1. Daily Workflow: Present the exact intake and assignment rhythm to the BiPlus team. 2. Policy Alignment: Draft and propose a unified communication guideline for BiPlus to handle direct messages and enforce ticketing discipline.
Day 2 | Understand Main Request Types: - Setup processes for product, price, promotion, voucher, and stock. - Internal self-checks before completion. | 1. What are the most common human or system errors encountered when setting up pricing and promotions, and how can they be avoided? 2. When should a Merchandising Sub-Lead review the ticket before QA? 3. For new product setups, what are the mandatory fields or attributes that most frequently cause system rejections or delays? 4. When setting up complex campaigns (stacking vouchers/discounts), what steps ensure the final price doesn't drop below the allowed margin? 5. What is the procedure for handling stock discrepancies and ensuring vouchers don't exceed allocated inventory? | 1. SOP Alignment: Update BiPlus's Execution Guides for the 5 main request types to fully align with SDSAP's actual operations. 2. Training Update: Update the BiPlus onboarding materials with the newly collected Common Errors Log and standard templates.
Day 3 | Handle Harder Situations & Special Stores: - Urgent requests, escalations, launches. - Bulk updates, AEM and Shop App content. - Special stores: EPP, SMB, O2O, 3PD. | 1. What is the exact escalation matrix for urgent requests, and who holds the final approval for immediate system changes? 2. During major product launches, how does the team synchronize the AEM content and Shop App updates to ensure they go live simultaneously? 3. What are the key setup differences (e.g., pricing, visibility, product allocation) between special stores like EPP, O2O, 3PD, and standard stores? 4. When performing bulk updates, what are the best practices or formatting tips for reviewing mass upload files to prevent widespread errors? 5. If an urgent setup issue occurs immediately after a launch, what is the standard rollback or quick-fix procedure? | 1. Escalation Protocol: Establish a clear, localized escalation pathway for BiPlus based on the SDSAP model. 2. Market Nuance Training: Conduct a training session for the BiPlus team on the specific differences and nuances when setting up for each market (based on observed live tickets).
Day 4 | Manage Backlog & Peak Days: - Review open tickets and pending work by market. - Peak preparation (11.11, Black Friday, Cyber Monday). - Backlog routines, tools, and filters. | 1. How does the Merch team initiate system freezes or prepare standard setups ahead of Mega Sales like 11.11 or Black Friday? 2. What is the contingency plan when ticket volume significantly exceeds the team's capacity during these peak days? 3. What are the primary bottlenecks or dependencies that typically cause Merch tickets to become stuck in "pending" or "open" status? 4. Do the current specific tools, system filters, or dashboards help you monitoring and managing the daily backlog? 5. How do you manage expectations and communicate with local market stakeholders when their non-urgent requests are delayed due to a high backlog? | 1. Backlog Optimization: Reconfigure BiPlus's daily Jira/ticketing filters and dashboards to match SDSAP's efficiency standards. 2. Peak Readiness Plan: Draft a structured preparation and contingency plan for BiPlus ahead of the next major Mega Sale.

## Trangdtt
Master plan: Trangdtt - SubLead Merchandise Market: Vietnam
Day | Time | Main activity | BiPlus does | SDSAP does | RHQ does | Done when | Status
Day 1 | Goal: See how the COE runs: intake, triage, assignment and the daily rhythm.
| 09:30 to 10:00 | Welcome | BiPlus visit lead and Service Delivery Manager meet the SDSAP COE lead: site and data rules, pairs. | Short welcome; introduce the counterparts. | None. | Everyone is seated with a counterpart. | Planned
| 10:00 to 17:00 | Daily operation | Service Delivery Manager sits beside the person who triages: how requests arrive, priority, assignment, follow-ups, shift handoffs. | Work as normal. | None. | Intake to close observed for the COE. | Planned
| 09:30 to 17:00 | Team queues | Tech Lead, QA Lead and Merchandising Sub-Leads sit beside the SDSAP leads of their teams: how work is picked up, done, checked and closed. | Work as normal. | None. | Daily work observed for Merchandising, Tech and QA. | Planned
| 09:30 to 15:30 | Markets | Merchandising Sub-Leads sit beside the person who handles each market: live queue, requesters, channels, language. | Work as normal. | None. | Live queue seen for all eight markets. | Planned
Day 2 | Goal: See the main request types done on live tickets.
| 09:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe product, price, promotion, voucher and stock setup for each market, and the checks before QA. | Work as normal. | None. | Main request types observed for each market. | Planned
| 09:30 to 15:30 | Tech | Tech Lead and Tech Sub-Lead observe configuration requests and production change (PC) tickets. | Work as normal. | None. | Configuration and change observed. | Planned
| 09:30 to 15:30 | QA | QA Lead and QA Sub-Lead observe QA checks and returns to Merchandising. | Work as normal. | None. | QA checks and returns observed. | Planned
| 09:30 to 12:30 | Operations | Service Delivery Manager observes SLA monitoring, follow-up of tickets waiting on Samsung L2/L3, and approvals (PC, Knox). | Work as normal. | Available online for questions BiPlus should not take to SDSAP. | SLA monitoring and approvals observed. | Planned
Day 3 | Goal: See the harder situations: urgent requests, escalations, launches.
| 09:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe urgent requests, bulk updates, AEM and Shop App content, and EPP, SMB, O2O and 3PD store requests. | Work as normal; call the BiPlus person over when an urgent or unusual request comes in. If there is no urgent request, reopen some previous requests to explore. | None. | Urgent and bulk work observed. | Planned
| 09:30 to 15:30 | Tech | Tech Lead and Tech Sub-Lead observe order issues, integrations, escalation to Samsung L2/L3 and account requests. | Work as normal; let BiPlus sit in on escalations. | None. | Order issues and escalation observed, if they occur. | Planned
| 09:30 to 15:30 | QA | QA Lead and QA Sub-Lead observe a BVT or a sanity test, if one runs this week. | Work as normal; let BiPlus sit in on a BVT or sanity test, if one runs. | None. | BVT or sanity test observed, if one runs. | Planned
| 09:30 to 17:00 | Operations and leadership | Service Delivery Manager observes urgent issues and incidents, if any. BiPlus visit lead sits in on RHQ or subsidiary calls with the COE, if any, listen only. | Let BiPlus listen in where suitable. | Agrees that BiPlus may listen in on RHQ calls with the COE this week. | Incident and call handling observed, if they occur. | Planned
Day 4 | Goal: See open work and how each market differs.
| 09:30 to 15:30 | Open work per market | Merchandising Sub-Leads observe open tickets and pending work for each market. Tech Lead and Tech Sub-Lead observe open Tech work by market. | Work as normal. | None. | Pending work seen for each market. | Planned
| 09:30 to 17:00 | Peak days | Merchandising and QA observe preparation for 11.11, Black Friday and Cyber Monday, and any launch this week. | Work as normal. | None. | Peak preparation observed. | Planned
| 09:30 to 12:30 | Backlog and tools | Service Delivery Manager observes how the backlog is reviewed, and the tools, filters and channels used every day. | Work as normal. | None. | Backlog routine and tools observed. | Planned
Day 5 | Goal: Fill in situations not seen yet; agree the November plan; close the visit.
| 09:30 to 12:30 | Situations not seen yet | Each BiPlus person observes the situations not yet seen during the week. | Work as normal. | None. | As many situations as possible observed. | Planned
| 14:00 to 15:30 | November plan: overlap and load ramp-up | BiPlus visit lead and the team Leads share what was observed and propose the load BiPlus takes in each of the four sprints, per team (Merchandising, Tech, QA), starting from the RHQ transition plan. | Confirms the work it keeps in each sprint, how it reviews BiPlus work during the overlap, and who covers 11.11, Black Friday and Cyber Monday. | Chairs the meeting. Agrees the load share for Sprints 1 to 4 per team, the SLA owner in each sprint, and the sprint rhythm: retrospective, improvements and plan for the next sprint. | Load ramp-up for the four sprints and the sprint rhythm agreed by RHQ, SDSAP and BiPlus, and written in the meeting note. | Planned
| 15:30 to 16:30 | Thank-you and wrap-up | BiPlus visit lead thanks SDSAP and asks for one contact per team for short questions until 30 November. | Name contacts, if willing. | Receives a short observation summary after the visit. | Visit closed. | Planned
After the visit | Goal: Use what was observed; take over the load sprint by sprint.
| To 30 November | Follow-up | Send a short observation summary to RHQ within one working day. Turn notes into BiPlus runbooks and training. | Answer short questions if contacted. | Forward questions to SDSAP if needed. | Observations used in Academy training and Sprint 1. | Planned
| End of each sprint (Sprints 1 to 4) | Sprint retrospective and plan | Present the sprint results (work taken over, SLA, quality, issues), the improvements for the next sprint, and the proposed load for the next sprint. | Gives feedback on BiPlus work in the sprint and confirms the work it hands over next. | Chairs the meeting. Agrees the improvements and the load share for the next sprint. | Next sprint plan agreed; every improvement has an owner. | Planned
Day | Main focus | What I should do | Key questions to ask SDSAP / current team | Output by end of day
Day 1 | Market map, queue ownership and ways of working | 1. Sit beside SDSAP Merchandising leads and the person handling each market. 2. Map each market owner, backup owner, requester group, language requirement and main communication channel. 3. Review live queue, open tickets, pending work and typical daily volume by market. 4. Observe how work is picked up, prioritised, assigned and tracked. 5. Confirm which requests are handled by Merchandising. | 1. Who owns each market today, and who is the backup? 2. Which channels are official for requests and escalations? 3. What makes a request urgent? 4. How do you decide what to pick up first? 5. Which markets are most complex and why? 6. Where do tickets commonly get delayed? 7. What information must be present before a merchandiser can start? 8. What will a handoff note have? If a ticket is almostly run out of SLA, the current PIC will continuously finish before leave or assign back the next shift? 9. When setting up new SKUs, if super sync failed and needs N-ERP to setup first, which status of the ticket and who is assignee? | Market ownership map. Queue and channel summary. Initial risk list by market. List of top request types and peak periods.
Day 2 | End-to-end merchandising execution and pre-QA checks | 1. Follow several real tickets from pickup to closure. 2. Observe setup steps for product, price, promotion, voucher and stock. 3. Capture the internal checks completed before sending to QA. 4. Compare differences between markets, especially language, requester style and approval flow. 5. Document common mistakes, rework reasons and quality gates. | 1. What are the required inputs for product setup? 2. What are the required checks for price, promotion and voucher setup? 3. How do you confirm stock or availability is correct? 4. What must be checked before handing work to QA? 5. Which fields or steps cause the most defects? 6. When should a Merchandising Sub-Lead review the ticket before QA? 7. What evidence or screenshots must be attached before closure? 8. Do we have any tools to pre-check the resolution? 9. What are the most common human or system errors encountered when setting up pricing and promotions, and how can they be avoided? | End-to-end workflow notes. Pre-QA checklist draft. Common defect and rework list. Examples of good ticket evidence.
Day 3 | Urgent requests, bulk work, content channels and launch readiness | 1. Observe urgent request handling and escalation behaviour. 2. Review bulk update process, validation method and rollback approach. 3. Observe AEM and Shop App content handling. 4. Review EPP, SMB, O2O and 3PD store request differences. 5. Check preparation status for 11.11, Black Friday, Cyber Monday and launches this week. 6. Align with QA and Tech on common handoff problems. | 1. How is urgent work approved and prioritised? 2. Who must be informed when urgent work arrives? 3. How do you validate bulk updates before and after execution? 4. What is the rollback process if a bulk update is wrong? 5. How is AEM work different from Shop App work? 6. What is different for EPP, SMB, O2O and 3PD store requests? 7. What launch items are not ready yet? 8. What must Merchandising confirm before QA and Tech can proceed? 9. What is the exact escalation matrix for urgent requests, and who holds the final approval for immediate system changes? | Urgent handling flow. Bulk update checklist. Content channel notes for AEM and Shop App. Launch readiness risk log. Cross-team handoff issues with QA and Tech.
Day 4 | Consolidation, transition recommendation and sprint load proposal | 1. Review all observations with SDSAP leads and BiPlus visit lead. 2. Validate assumptions, risks and missing knowledge. 3. Group work by complexity: safe to take, needs supervision, not ready yet. 4. Propose BiPlus load for each of the four one-week sprints per team: Merchandising, Tech and QA. 5. Agree immediate actions, owners and follow-up KT items. 6. Prepare final readout for team leads. | 1. Which work can BiPlus take in Sprint 1 with low risk? 2. Which work needs SDSAP supervision for one or two more weeks? 3. Which market or request type should not move yet? 4. What knowledge gaps must be closed before transition? 5. What daily control report should the Merchandising Sub-Lead own? 6. What escalation rules must be agreed before handover? 7. What does success look like after the first four sprints? | Final observation summary. Risk and dependency list. Four-sprint load proposal. Action list with owners and due dates.

## XuanTTT
Name: Xuan Trieu
Role: QA Lead
Market: SEAO (8 Markets)
Day 1 – Understand Daily QA Operations Goal: See how the COE runs: intake, assignment, and the daily operations.
QA Activities
Observe daily ticket intake, QA monitoring and assignment. Observe how QA-required tickets are identified and routed from Merchandising or Tech. Understand daily routines, shift handovers, and team coordination. Walk through the jira ticketing system, QA tools, and verification environments.
Key Questions
1. Which Merchandising services require QA verification, and when is QA required for Tech tickets?
2. How are QA tickets received, prioritized, assigned, and tracked?
3. What information and evidence must be provided before QA starts verification?
4. How does the team monitor SLA and manage ticket handovers between shifts?
5. What systems, dashboards, and tools are used in daily QA operations?
Information to Collect
1. QA scope and QA-gated service list.
2. QA workflow, ticket assignment rules, and handover procedures.
3. System/tool list, access requirements, and SLA monitoring dashboards.
Day 2 – Observe Actual QA Verification Goal: See the main request types done on live tickets.
QA Activities: Directly observe the verification of actual Pricing, Promotion, Voucher, and other QA-gated Merchandising tickets. Follow tickets through verification, PASS/FAIL decisions, evidence recording, and closure. Review how checklists, test scenarios, and SKU sampling rules are applied. Observe defect logging and re-checks where available.
Key Questions
1. Can you walk us through actual tickets for the most common QA-required services?
2. How do you determine test coverage and PASS/FAIL criteria for each service?
3. Which positive, negative, and edge-case scenarios are typically checked?
4. How is verification evidence recorded and attached to tickets?
5. What are the most common defects found during verification?
Information to Collect
1. Actual PASS/FAIL tickets with verification evidence.
2. QA checklists, test cases, acceptance criteria, and sampling rules.
3. Common defect patterns and recurring issues by service.
Day 3 – Handle Complex Cases and Escalations Goal: See the harder situations: urgent requests, escalations, launches.
QA Activities: Observe urgent and high-risk ticket verification, particularly pricing and promotion changes. Review actual FAIL → Fix → Re-check cases and escalation examples. Observe QA involvement in launch-related or time-sensitive changes. Review historical production incidents, focusing on defects that escaped QA verification.
Key Questions
1. How are urgent or high-risk tickets handled when the remaining SLA is limited?
2. How are repeated FAIL results, disagreements, and escalations managed?
3. What additional verification is required for major launches or high-risk promotions?
4. What defects have previously escaped QA and reached production?
5. What were the root causes, business impacts, and preventive actions for those production defects?
Information to Collect
1. Urgent/high-risk ticket examples and escalation records.
2. FAIL/Re-check history and incident examples.
3. Historical Escaped Defect List, including RCA, business impact, corrective and preventive actions.
4. High-risk test scenarios and lessons learned.
Day 4 – Review Open Work and Market Differences Goal: See open work and how each market differs.
QA Activities: Review the current QA backlog, outstanding tickets, pending re-checks, and unresolved issues. Check the follow-up of open tickets and coordination with Merchandising and Tech teams. Identify market-specific QA requirements, configurations, and verification scenarios. Review recurring defects, known issues, and operational challenges across markets.
Key Questions:
1. What QA tickets are currently open, pending, or blocked, and why?
2. How are pending tickets and unresolved defects tracked and followed up?
3. What are the major differences in QA verification between markets?
4. Which markets or services have the most recurring defects or operational challenges?
5. Are there any known issues, special configurations, or market-specific scenarios that QA should be aware of?
Information to Collect:
1. Current QA backlog and pending ticket list.
2. Market-specific verification rules, test scenarios, and known issues.
3. Recurring defect trends and outstanding risks.
4. Key contacts and coordination procedures by market.
Day 5 – Close Knowledge Gaps and Prepare for Transition Goal: Fill in situations not seen yet; agree the November plan; close the visit.
QA Activities: Request walkthroughs of any important QA scenarios not observed during Days 1–4. Review remaining gaps in QA workflows, tools, checklists, and verification knowledge. Consolidate collected defect patterns, escaped defects, and lessons learned. Review outstanding questions and dependencies with the current vendor.
Key Questions
1. Are there any critical QA services or scenarios we have not covered?
2. What additional knowledge, system access, or documentation is required before takeover?
3. What are the biggest risks or challenges for the incoming QA team?
4. What are the remaining open items, owners, and target dates for closure?
Information to Collect
1. Final QA knowledge gaps and outstanding questions.
2. Consolidated QA procedures, checklists, and sample tickets.
3. Common defect patterns and historical escaped defect records.
4. System access and documentation readiness checklist.
Documents & Artifacts to Collect, Verify, and Release After the Business Trip
1. QA Scope & Service Catalogue | List of QA-gated Merchandising services and selected Tech services requiring QA verification.
2. QA Operational SOP & End-to-End Workflow | Ticket intake, assignment, verification, PASS/FAIL, re-check, approval, and closure
3. QA Risk Classification & Verification Matrix | Risk levels, verification requirements, SKU coverage, and sampling rules.
4. QA Checklists & Test Case Library | Standard checklists, test scenarios, and acceptance criteria for each applicable service.
5. Actual QA Ticket Samples & Evidence | Real PASS/FAIL tickets, verification records, screenshots, and re-check history.
6. Common Defect Patterns & Recurring Issues Register | Frequent defects, root causes, trends, and lessons learned.
7. Historical Escaped Defect Register | Production defects missed by QA, including RCA, business impact, corrective actions, and preventive measures.
8. QA Tools, Environments & Access Matrix | Required systems, tools, environments, permissions, and access readiness.
9. SLA & Escalation Procedures | SLA monitoring, priority handling, escalation rules, and breach management.
10. QA Shift Handover & Daily Operations Guide | Shift coverage, handover procedures, and daily routines.
11. Market-Specific QA Requirements & Known Issues Register | Local verification rules, special scenarios, known limitations, and high-risk configurations.
12. QA Reporting & KPI Templates | Daily/weekly reports, verification volume, defect trends, quality metrics, and SLA performance.
13. QA Stakeholder & Escalation Contact Matrix | Key contacts, responsibilities, and coordination with subsidiaries teams.
14. QA KT Completion & Knowledge Gap Tracker | Topics covered, evidence collected, outstanding questions, missing documentation, and action owners.

## MinhVT
Master plan: MinhVT - Tech Team
Day | Time | Main activity | BiPlus does | SDSAP does | RHQ does | Done when | Questions | Information to collect | Status
Day 1 | Goal: See how the COE runs: intake, triage, assignment and the daily rhythm.
| 09:30 to 10:00 | Welcome | BiPlus visit lead and Service Delivery Manager meet the SDSAP COE lead: site and data rules, pairs. | Short welcome; introduce the counterparts. | None. | Everyone is seated with a counterpart. |  |  | Planned
| 10:00 to 17:00 | Daily operation | Service Delivery Manager sits beside the person who triages: how requests arrive, priority, assignment, follow-ups, shift handoffs. | Work as normal. | None. | Intake to close observed for the COE. |  | 1. Map the owner and backup for each market 2. Understand the live COEC queue, ticket volume by type and market, and aging tickets 3. Find the root causes of Tech SLA misses 4. Confirm the official request and escalation channels 5. Verify the team's system access | Planned
| 09:30 to 17:00 | Team queues | Tech Lead, QA Lead and Merchandising Sub-Leads sit beside the SDSAP leads of their teams: how work is picked up, done, checked and closed. | Work as normal. | None. | Daily work observed for Merchandising, Tech and QA. |  |  | Planned
| 09:30 to 15:30 | Markets | Merchandising Sub-Leads sit beside the person who handles each market: live queue, requesters, channels, language. | Work as normal. | None. | Live queue seen for all eight markets. |  |  | Planned
Day 2 | Goal: See the main request types done on live tickets.
| 09:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe product, price, promotion, voucher and stock setup for each market, and the checks before QA. | Work as normal. | None. | Main request types observed for each market. |  |  | Planned
| 09:30 to 15:30 | Tech | Tech Lead and Tech Sub-Lead observe configuration requests and production change (PC) tickets. | Work as normal. | None. | Configuration and change observed. |  |  | Planned
| 09:30 to 15:30 | QA | QA Lead and QA Sub-Lead observe QA checks and returns to Merchandising. | Work as normal. | None. | QA checks and returns observed. |  |  | Planned
| 09:30 to 12:30 | Operations | Service Delivery Manager observes SLA monitoring, follow-up of tickets waiting on Samsung L2/L3, and approvals (PC, Knox). | Work as normal. | Available online for questions BiPlus should not take to SDSAP. | SLA monitoring and approvals observed. |  |  | Planned
Day 3 | Goal: See the harder situations: urgent requests, escalations, launches.
| 09:30 to 17:00 | Merchandising | Merchandising Sub-Leads observe urgent requests, bulk updates, AEM and Shop App content, and EPP, SMB, O2O and 3PD store requests. | Work as normal; call the BiPlus person over when an urgent or unusual request comes in. If there is no urgent request, reopen some previous requests to explore. | None. | Urgent and bulk work observed. |  |  | Planned
| 09:30 to 15:30 | Tech | Tech Lead and Tech Sub-Lead observe order issues, integrations, escalation to Samsung L2/L3 and account requests. | Work as normal; let BiPlus sit in on escalations. | None. | Order issues and escalation observed, if they occur. |  |  | Planned
| 09:30 to 15:30 | QA | QA Lead and QA Sub-Lead observe a BVT or a sanity test, if one runs this week. | Work as normal; let BiPlus sit in on a BVT or sanity test, if one runs. | None. | BVT or sanity test observed, if one runs. |  |  | Planned
| 09:30 to 17:00 | Operations and leadership | Service Delivery Manager observes urgent issues and incidents, if any. BiPlus visit lead sits in on RHQ or subsidiary calls with the COE, if any, listen only. | Let BiPlus listen in where suitable. | Agrees that BiPlus may listen in on RHQ calls with the COE this week. | Incident and call handling observed, if they occur. |  |  | Planned
Day 4 | Goal: See open work and how each market differs.
| 09:30 to 15:30 | Open work per market | Merchandising Sub-Leads observe open tickets and pending work for each market. Tech Lead and Tech Sub-Lead observe open Tech work by market. | Work as normal. | None. | Pending work seen for each market. |  |  | Planned
| 09:30 to 17:00 | Peak days | Merchandising and QA observe preparation for 11.11, Black Friday and Cyber Monday, and any launch this week. | Work as normal. | None. | Peak preparation observed. |  |  | Planned
| 09:30 to 12:30 | Backlog and tools | Service Delivery Manager observes how the backlog is reviewed, and the tools, filters and channels used every day. | Work as normal. | None. | Backlog routine and tools observed. |  |  | Planned
Day 5 | Goal: Fill in situations not seen yet; agree the November plan; close the visit.
| 09:30 to 12:30 | Situations not seen yet | Each BiPlus person observes the situations not yet seen during the week. | Work as normal. | None. | As many situations as possible observed. |  |  | Planned
| 14:00 to 15:30 | November plan: overlap and load ramp-up | BiPlus visit lead and the team Leads share what was observed and propose the load BiPlus takes in each of the four sprints, per team (Merchandising, Tech, QA), starting from the RHQ transition plan. | Confirms the work it keeps in each sprint, how it reviews BiPlus work during the overlap, and who covers 11.11, Black Friday and Cyber Monday. | Chairs the meeting. Agrees the load share for Sprints 1 to 4 per team, the SLA owner in each sprint, and the sprint rhythm: retrospective, improvements and plan for the next sprint. | Load ramp-up for the four sprints and the sprint rhythm agreed by RHQ, SDSAP and BiPlus, and written in the meeting note. |  |  | Planned
| 15:30 to 16:30 | Thank-you and wrap-up | BiPlus visit lead thanks SDSAP and asks for one contact per team for short questions until 30 November. | Name contacts, if willing. | Receives a short observation summary after the visit. | Visit closed. |  |  | Planned
After the visit | Goal: Use what was observed; take over the load sprint by sprint.
| To 30 November | Follow-up | Send a short observation summary to RHQ within one working day. Turn notes into BiPlus runbooks and training. | Answer short questions if contacted. | Forward questions to SDSAP if needed. | Observations used in Academy training and Sprint 1. |  |  | Planned
| End of each sprint (Sprints 1 to 4) | Sprint retrospective and plan | Present the sprint results (work taken over, SLA, quality, issues), the improvements for the next sprint, and the proposed load for the next sprint. | Gives feedback on BiPlus work in the sprint and confirms the work it hands over next. | Chairs the meeting. Agrees the improvements and the load share for the next sprint. | Next sprint plan agreed; every improvement has an owner. |  |  | Planned
| Questions for SDSAP Tech | Information to collect
A | Ownership and team
1 | Who owns each market today, and who is the backup? | Owner and backup for each market. Team A: VN, TH, ID, NZ. Team B: SG, MY, PH, AU
2 | How many people are on the Tech team? What are their shifts and working hours? | Team size and roles, shift pattern, working hours in SGT and ICT, who covers nights and weekends
3 | Which markets or request types are the most complex, and why? | List of high-risk markets and request types, with reasons
4 | Welcome session | Name, role and contact of the SDSAP Tech counterpart; site and data rules
B | Pick-up and triage
5 | How does a ticket reach Tech: directly in COEC, routed by triage, linked from Merchandising, or by email or chat? | Intake channels and how often each is used; the official escalation channel
6 | How do you decide what to pick up first? Who sets or corrects the priority? | Rules for priority and pick-up order; who is allowed to change priority
7 | How are tickets assigned: by market, by skill, or by whoever is free? | Assignment method and who assigns
8 | What information must a ticket have before Tech can start? | Minimum input checklist for a Tech ticket
9 | COEC queue walkthrough | Queue snapshot: open tickets by status, priority and market; aging tickets; tickets in ON HOLD and SYSTEM SUPPORT
10 | Which filters, boards and dashboards do you open first each morning? | Names and links of the filters, boards and dashboards used every day
C | Doing the work
11 | What are the most common Tech ticket types, and roughly how many per day? | Daily volume; the top 5–10 Tech request types
12 | Which tasks follow a standard runbook, and which need investigation or scripting? | Split between runbook-based and investigation work, to use for the Level 1 / Level 2 split
13 | Which tools do you use most each day: Backoffice, HAC, FlexibleSearch, ImpEx, Groovy, Kibana? | Tools used, and which ones need production access
14 | Following tickets in progress | How the real workflow compares with TC-03: NEW → ASSIGNED → IN REVIEW → IN PROGRESS → QA REVIEW → LAUNCH VERIFICATION
D | Checking and closing
15 | Who checks a change before it goes to production? Is there a second check before the PC ticket? | How changes are checked today: self-QA, second check, Tech Lead review
16 | How long does a PC ticket usually wait for approval? What happens to urgent ones? | Usual PC approval time; how urgent PC tickets are handled; who approves while Oliver is away
17 | When is a ticket considered done: at LAUNCH VERIFICATION or at CLOSED? Who confirms? | Definition of done and who confirms it
18 | What evidence must be on the ticket before it is closed? | Evidence checklist; example tickets with good evidence (ticket keys only)
E | Handoffs and escalation
19 | How do you hand over between shifts, and where is the handover recorded? | How shift handover works, which template is used, where it is recorded
20 | When do you escalate to Samsung L2/L3 (SDS India), and how do you follow up? | Criteria for escalating, L2/L3 contacts, how often to follow up
21 | How do you coordinate with Merchandising on linked tickets, and with QA or BVT? | Handoff points and problems with Merchandising and QA/BVT
22 | Check with the SDM and Merchandising Sub-Leads | How triage routes tickets to Tech; how wrong-team tickets are handled; which Merchandising tickets wait for Tech
F | SLA and risk
23 | Where do Tech tickets usually get delayed or break SLA? | Main causes of SLA breaches; the waiting statuses where tickets stay longest
24 | How do you track the SLA clock: with a plug-in, a filter, or manually? | How SLA is tracked and how alerts are sent
25 | Which tickets are currently aging or at risk? | List of tickets at risk (keys only)
26 | End-of-day wrap-up | First risk list; open questions for Day 2 and later

## NgaVT
Nga - QA
| Plan detail | Artifacts
Ngày 1 – Tổng quan vận hành
What are the main objectives?
Understand the overall operation process by observing how the Malaysia team handles real tickets.
Understand where QA fits into the ticket workflow, who is responsible for QA, how many tickets QA handles per day, and the main request types reviewed by QA.
What questions need to be included in the survey?
1 | Where does QA sit in the ticket workflow? At which status does a ticket come to QA, and where does it go after QA?
2 | Who does QA today? How many people, which shifts, which markets does each person cover?
3 | Roughly how many tickets does QA review per day, and which request types make up most of them?
4 | Which request types go through QA Review, and which skip QA? Who decides this, and is it written down?
5 | How does QA pick up tickets - assigned by a lead, or from a queue or dashboard?
6 | What tools and environments does QA use (Promotion Simulator, Backoffice, storefront, Jira dashboards)?
Bàn giao ca / kíp:
1 | How do you hand over work between shifts or between team members? Is there a handover meeting, a handover note, or a shared Jira filter?
2 | What does a handover cover - tickets still in QA Review, tickets waiting for a go-live check, promotions launching overnight, open escalations?
3 | Who covers QA outside working hours (nights, weekends, public holidays)? How are promotions that go live at midnight checked?
4 | When someone is absent, how is their QA queue reassigned? Is there a named backup?
5 | Has anything been missed during a handover before? What happened, and what did you change?
What information/content needs to be collected?
1 | Sơ đồ luồng ticket có QA: trạng thái vào, trạng thái ra, trạng thái khi fail.
2 | Nhân sự QA hiện tại: số người, ca làm việc, thị trường phụ trách.
3 | Khối lượng ticket QA mỗi ngày và các request type chiếm nhiều nhất.
4 | Danh sách request type cần QA review và không cần.
5 | Danh sách công cụ, dashboard, bộ lọc Jira QA đang dùng.
6 | Cách bàn giao ca/kíp hiện tại: thời điểm, hình thức (họp, note, bộ lọc Jira), mẫu handover nếu có.
7 | Nội dung bắt buộc trong một lần bàn giao (ticket đang QA, ticket chờ kiểm tra go-live, promotion launch qua đêm, escalation đang mở).
8 | Cách cover QA ngoài giờ, cuối tuần, ngày lễ và promotion live lúc nửa đêm.
9 | Cơ chế backup khi có người vắng.
Ngày 2 – Các request type và cách xử lý
What are the main objectives?
For each request type that requires QA in the 19 priority services (Shop Merchandising), understand who receives the ticket, what QA needs to check, who QA reports the results to, and how QA communicates with the Merchandising team and local markets.
Confirm with the Malaysia team whether the QA steps, checking methods, and test cases documented in the 19-service file match the actual process
What questions need to be included in the survey?
Hỏi cho từng request type:
1 | What exactly does QA check for this request type? Is there a checklist?
2 | Can you walk me through one real ticket, step by step? (Chụp màn hình từng bước.)
3 | Are these the right test cases for this request type? Is anything missing? (Đối chiếu với file 32 service.)
4 | What evidence do you attach, in what format (screenshot, PowerPoint, video link), and where (Jira, Confluence)?
5 | When QA finds a problem, how is it sent back to Merchandising - which status, which comment format?
6 | Who does QA talk to directly - Merchandising, Tech, the market, RHQ? Through which channel?
7 | How long does QA usually take for this request type?
What information/content needs to be collected?
1 | Checklist QA cho từng request type, đã được đối tác xác nhận hoặc bổ sung.
2 | Danh sách test case từng tình huống, đánh dấu đã xác nhận hay còn thiếu.
3 | Ảnh chụp màn hình từng bước QA trên ticket thật, để đưa vào runbook.
4 | Mẫu bằng chứng QA đạt chuẩn: định dạng, nơi lưu, cách đặt tên.
5 | Cách trả ticket về khi fail: trạng thái, mẫu comment.
6 | Người và kênh QA giao tiếp hằng ngày.
7 | Thời gian QA trung bình theo từng request type.
Ngày 3 – Tình huống sâu: request gấp, escalation, launch
What are the main objectives?
Understand how QA handles urgent requests, failed tickets, escalations, launches, and post-go-live checks.
Understand the key QA risks and quality control checkpoints (Ms. Xuan is mainly responsible for this)
Understand the rules for updating ticket statuses after QA to avoid SLA violations.
What questions need to be included in the survey?
1 | How does QA handle a promotion that must go live tonight? What is skipped, and who takes responsibility?
2 | What happens when a ticket fails QA twice? Is the root cause recorded anywhere?
3 | When should QA escalate (for example sync failure, missing information), to whom, with what information, and how do you follow up?
4 | After a promotion goes live, who checks it on live, at what time, and how is it confirmed on the ticket?
5 | For a ticket with several promotions launching on different dates, how is QA done for each launch?
6 | After QA, who moves the ticket to the subsidiary-side status so the SLA clock stops? What are the most common SLA mistakes?
7 | What errors does QA catch most often? Which errors have reached production, and what did you change afterwards?
What information/content needs to be collected?
1 | Ma trận escalation: tình huống → báo ai → kèm thông tin gì → follow-up thế nào.
2 | Quy trình xử lý request gấp / last-minute.
3 | Quy trình kiểm tra sau go-live và cách xác nhận trên ticket.
4 | Quy tắc đổi trạng thái sau QA và các lỗi SLA hay gặp.
5 | Danh sách lỗi thường gặp và lỗi đã lọt ra production - đưa vào Known Error.
6 | Danh sách điểm chốt chặn bắt buộc kiểm tra trước khi pass.
Ngày 4 – Từng thị trường
What are the main objectives?
Understand the QA process for the assigned market, including peak and off-peak periods, key contacts, and common issues.
Work closely with the assigned market team to understand their daily operations and be able to answer relevant QA questions.
What questions need to be included in the survey?
1 | When are this market's peak periods? How does QA workload change then?
2 | Which QA rules are unique to this market (promotion types, pricing, approvals)?
3 | Who in this market does QA work with, and how do they prefer to communicate?
4 | What errors happen most often for this market?
5 | Does this market check results itself after launch, or rely fully on CoE?
What information/content needs to be collected?
1 | Thời điểm cao điểm và thấp điểm của thị trường.
2 | Quy tắc QA riêng của thị trường - cập nhật vào Market Note.
3 | Người liên hệ và kênh giao tiếp.
4 | Các lỗi hay gặp của thị trường.

## Lists (hidden)
Drop-down lists (do not edit)
Activity status | Observed on
Planned | Day 1
Done | Day 2
Partly done | Day 3
Moved | Day 4
Day 5
Not seen